## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
ACESSE (M) SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | NG ZHI QING | AARON TSEN | 2021-12-31 | 2022-02-28 | 2022-03-09 | 40 | 2022-03-09 | REVIEWING - MANAGER | Clearing Mr Eric review @ 4/7/22 | 2022-03-01
ACESSE (M) SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-02-28 | 2022-03-15 | 16 | 2022-03-15 | WIP |  | 2022-02-28
ARCHITUDE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-05-18 | 2022-07-31 | 48 | 2022-06-21 | REVIEWING - MANAGER |  | 2022-06-07
ARCHITUDE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-05-18 | 2022-07-31 | 8 | 2022-06-21 | WIP |  | 2022-06-08
CENTA INVESTMENT LIMITED | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW, AARON TSEN | 2021-12-31 | 2022-06-01 | 2022-06-30 | 24 | 2022-06-27 | REVIEWING - PARTNER | Sent to Kaizen @ 29-6-22 | 2022-06-13
CRAWFORT SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-28 | 2022-07-31 | 32 | 2022-05-31 | WIP | WIP - to further sent further queries by 7.7.2022 | 2022-05-18
CRAWFORT SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-28 | 2022-07-31 | 8 | 2022-05-31 | WIP |  | 2022-05-20
DE POP ASIA DISTRIBUTOR | ACUMEN ALPHA ADVISORY SDN BHD | ACCOUNTING | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-30 | 2022-04-05 | 24 | 2022-04-05 | WIP | Account key up to April'22. To confirm with client on Stock import system. @ 5.7.2022 | 2022-03-31
FARM ESTABLISHMENTS SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | AARON TSEN | 2021-12-31 | 2022-04-07 | 2022-06-30 | 40 | 2022-06-03 | FINALIZING | Rennie reviewed @ 24/6/2022; pending finalising by Aaron | 2022-05-23
FARM ESTABLISHMENTS SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | AARON TSEN | 2021-12-31 | 2022-04-07 | 2022-07-31 | 16 | 2022-06-13 | WIP |  | 2022-05-21
FAST MONEY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | HWEE XIN LIM | AARON TSEN | AARON TSEN | 2021-12-31 |  |  | 40 | 2022-03-18 | PENDING PAYMENT |  | 2022-03-01
FORWARD 50 SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-05-18 | 2022-07-31 | 56 | 2022-06-30 | WIP | To clear Chloe review | 2022-06-14
FORWARD 50 SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-05-18 | 2022-07-31 | 16 | 2022-06-30 | WIP |  | 2022-06-16
HOKI 146 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-09-30 | 2022-03-16 | 2022-03-22 | 16 | 2022-03-22 | PENDING PAYMENT | Sent to Pei San to obtain director signature @ 25 Apr 2022 | 2022-03-16
HOKI 146 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-09-30 | 2022-03-16 | 2022-03-22 | 8 | 2022-03-22 | PENDING PAYMENT | Sent to Pei San to obtain director signature @ 25 Apr 2022 | 2022-03-14
KAZHOU PTE. LTD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | AARON TSEN, JIVAN SR | 2021-12-31 | 2022-04-01 | 2022-04-30 | 96 | 2022-04-30 | REVIEWING - PARTNER | SA Assurance received @ 20-7-22; Done reviewed by Mr Ray @ 18-7-22 | 2022-04-04
KNT OFFSHORE MARINE SERVICES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-18 | 2022-03-28 | 16 | 2022-03-28 | PENDING PAYMENT | Sent to client @ 29 Apr 2022 | 2022-03-23
KNT OFFSHORE MARINE SERVICES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-18 | 2022-03-28 | 8 | 2022-03-28 | WIP | Sent to client @ 29 Apr 2022 | 2022-03-18
KYROX SDN BHD | ACUMEN ALPHA ADVISORY SDN BHD | ACCOUNTING | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-23 | 2022-03-30 | 16 | 2022-03-30 | WIP | Done update to Nov'21. | 2022-03-23
MAIN PLACE MC | ACUMEN ALPHA ADVISORY SDN BHD | ACCOUNTING | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2022-02-28 | 2022-03-04 | 2022-03-28 | 16 | 2022-03-28 | PENDING PAYMENT | Done. Apr'22 | 2022-03-23
MAIN PLACE MC | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-04 | 2022-04-22 | 40 | 2022-04-22 | WIP | Transferred to Rennie. | 2022-03-23
MINEXPORT SDN BHD | ACUMEN ALPHA ADVISORY SDN BHD | ACCOUNTING | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-04-20 | 2022-05-31 | 24 | 2022-05-23 | FINALIZING | Close case 31/5/22 | 2022-04-22
PROCONST PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | JING HE TAN | 2021-12-31 | 2022-03-02 | 2022-03-21 | 18 | 2022-03-21 | REVIEWING - MANAGER | ECI - YA2022 JINGHE 2 MAR / TAX COMP FORM C AARON 14-15 MAR | 2022-03-22
PROCONST PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-02 | 2022-03-18 | 16 | 2022-03-18 | REVIEWING - MANAGER | Submitted to review | 2022-03-14
SLR SYNERGIES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-31 | 2022-04-04 | 24 | 2022-04-04 | REVIEWING - MANAGER |  | 2022-04-01
SLR SYNERGIES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-31 | 2022-04-04 | 24 | 2022-04-04 | WIP |  | 2022-04-01
TIGER CONSULTING SDN BHD | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | AARON TSEN | 2021-12-31 | 2022-03-28 | 2022-06-30 | 56 | 2022-05-19 | PENDING DOCS & PAYMENT | To clear review point from Mr Eric | 2022-05-05
TIGER CONSULTING SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | AARON TSEN | AARON TSEN | 2021-12-31 | 2022-03-28 | 2022-07-31 | 16 | 2022-05-20 | WIP |  | 2022-05-12