## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
2J HOLDINGS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG | 2021-03-31 | 2021-08-16 | 2021-09-30 | 80 | 2021-08-31 | ACCOUNT NOT IN |  | 2021-08-17
A&O FARMERS PTE. LTD. |  | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | KWEH CHUN SHENG, LOK YEE RENNIE THEW | 2021-03-31 | 2021-08-16 | 2021-09-30 | 40 | 2021-08-27 | WIP | Queries raised and sent by 19-8-21; Queries replied by Mr Thomas @ 20-8-21 (partial); **Pending the 5Q(queries) replied from Siew Ee | 2021-08-17
ASIA PACIFIC BIOINFORMATICS NETWORK LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | MUI LING TAN | MUI LING TAN | 2020-12-31 | 2021-05-19 | 2021-06-30 | 40 | 2021-06-16 | REVIEWING - MANAGER |  | 2021-06-07
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG, YING QIN YONG | 2020-12-31 | 2021-01-25 | 2021-04-30 | 40 | 2021-07-31 | PENDING PAYMENT | Send out for adoption: 28 July 2021 | 2021-01-25
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG, YING QIN YONG, JOANNE TEH HUI LING | 2020-12-31 | 2021-03-29 | 2021-04-30 | 80 | 2021-04-16 | SIGNED | Sent for adoption: 28 July 2021 | 2021-03-29
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | JOANNE TEH HUI LING, PIK EN TOH | 2020-12-31 | 2021-02-03 | 2021-04-30 | 80 | 2021-07-31 | PENDING PAYMENT | To submit on 21 July | 2021-02-03
BL PROJECTS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG | 2020-12-31 | 2021-07-02 | 2021-06-30 | 90 | 2021-08-31 | YET TO START | Yet to start. Planning meeting with partner on 18.08. Updated on 22.08 | 2021-08-02
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | YU XUEN NG | 2019-12-31 | 2020-10-12 | 2020-11-30 | 60 | 2021-03-15 | PENDING DOCS | Follow up on 18/7 | 2020-10-29
CONVERSANT GLOBAL PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-08 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | Finalising working paper and draft report | 2021-03-23
CONVERSANT INVESTMENT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | XUN HUI SOH | XUN HUI SOH, SU HUI TAN | 2019-12-31 | 2020-05-22 | 2020-06-30 | 20 | 2021-03-12 | PENDING DOCS | Sent out adoption on 14 Oct Sent for partner review in softcopy on 26 June | 2020-06-05
CONVERSANT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-11 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | To work on cosolidation | 2021-03-23
CONVERSANT SOLUTIONS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | MUI LING TAN, YU XUEN NG, PIK EN TOH | 2020-12-31 | 2021-03-03 | 2021-06-30 | 100 | 2021-07-31 | SENT OUT FOR ADOPTION | Finishing draft FS | 2021-03-24
GLOBAL OCEANLINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, SOO WUEN ONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 140 | 2021-08-31 | PLANNING WITH ACCOUNT |  | 2021-08-02
GM CREDITZ PTE. LTD. | ACUMEN ASSURANCE | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2020-12-31 | 2021-01-25 | 2021-04-30 | 40 | 2021-06-04 | FINALIZING | Selected samples and sent for client to prepare | 2021-01-25
GM CREDITZ PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | YING QIN YONG, JOANNE TEH HUI LING, PUI SHI LEE | 2020-12-31 | 2021-03-01 | 2021-04-30 | 80 | 2021-03-30 | SENT OUT FOR ADOPTION | Mapping done | 2021-03-24
HDR PAYMENT PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-06-11 | 2021-08-31 | 100 | 2021-08-31 | PENDING DOCS | Extension filed Audit for 2019 (opening) and 2020 | 2021-08-01
HDR SG PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-06-11 | 2021-08-31 | 8 | 2021-08-06 | REVIEWING - MANAGER | 2 MTHS EXTENSION FILED FIRST SET OF FS | 2021-08-01
HHL CREDIT PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH |  |  |  | 24 | 2021-06-02 | FINALIZING | To print working paper and submit to partner | 2020-08-20
HS CREDIT PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | WOELLY WILLIAM | PAI NEE WONG | XUN HUI SOH | PIK EN TOH |  |  |  | 8 |  | ACCOUNT NOT IN | PMFT AUDIT - DIRECTOR ASK TO PUT ON HOLD FIRST AND WAIT FOR THEIR FURTHER INSTRUCTION ON OUR QUERIES | 2020-01-01
LMB AEROSPACE ASIA PACIFIC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2021-06-30 | 2021-07-06 | 2021-12-31 | 60 | 2021-08-31 | PLANNING WITH ACCOUNT |  | 2021-07-26
LUMIPLAN ASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YING QIN YONG | YING QIN YONG | 2021-03-31 | 2021-06-17 | 2021-09-30 | 60 | 2021-07-30 | WIP |  | 2021-07-23
NOVEL COMMUNICATION PTE. LTD. | SYA PAC | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, KOK YEE CHOONG | 2020-12-31 | 2021-05-07 | 2021-06-30 | 110 | 2021-06-23 | WIP | Fieldwork start on 12.08.21 | 2021-06-10
NUTRIXPERTS PTE. LTD. (FORMERLY KNOWN AS LISA RD SINGAPORE PTE. LTD.) | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-09-03 | 2020-09-30 | 40 | 2021-04-30 | KIV | Sent audit queries to client on 19 August 21 | 2020-09-07
PROCESS TECHNOLOGY CONSULTANTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | WEI QI YU, XUN HUI SOH | 2021-03-31 | 2021-06-09 | 2021-09-30 | 60 | 2021-07-30 | CLEARING REVIEW POINTS | 1. Account received on 9 June 2021 | 2021-06-25
SCDA ARCHITECTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | YONG LAI WONG, CHIA EN CHEONG, CHIN YING CHEW | 2020-12-31 | 2021-04-21 | 2021-06-30 | 120 | 2021-05-21 | PENDING PAYMENT | Fieldwork started on 10.05.21 Report signed on 27.07.21 Updated on 02.08.21 | 2021-05-03
SCDA DESIGN PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | YONG LAI WONG, CHIN YING CHEW, CHIA EN CHEONG | 2020-12-31 | 2021-04-21 | 2021-06-30 | 100 | 2021-05-21 | PENDING PAYMENT | Fieldwork started on 10.05.21 File submitted for review - 04.06.21 Report signed on 27.07.21 Updated on 02.08.21 | 2021-05-03
SCDA INTERIORS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | YONG LAI WONG, CHIN YING CHEW, CHIA EN CHEONG | 2020-12-31 | 2021-04-21 | 2021-06-30 | 80 | 2021-05-21 | PENDING PAYMENT | Fieldwork started on 10.05.21 Report signed on 27.07.21 Updated on 02.08.21 | 2021-05-03
SGP CREDIT SINGAPORE PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | SOO WUEN ONG | JOANNE TEH HUI LING, SOO WUEN ONG | 2020-12-31 | 2021-03-01 | 2021-04-30 | 80 | 2021-03-19 | SIGNED | Pending audit programme filling | 2021-03-16
SUPREME LINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 70 | 2021-08-31 | WIP |  | 2021-08-02
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-11-04 | 2020-11-30 | 70 | 2021-03-31 | PENDING DOCS | All copies signed, pending cor sec document to be received. | 2020-11-23
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | YU XUEN NG, SOO WUEN ONG | 2020-12-31 | 2021-03-09 | 2021-06-30 | 80 | 2021-07-31 | SENT OUT FOR ADOPTION | To sent for adoption with other companies | 2021-03-23
TECHNIDRILL AUSTRALASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | JOANNE TEH HUI LING, CHEA CHEI LOH | 2020-12-31 | 2021-03-29 | 2021-03-29 | 80 | 2021-05-14 | PENDING DOCS | 1. Send out adoption on 30 June 2021 Email d.siervo@altios.com (Donnabelle Siervo) CC g.derostolan@altios.com (Geraldine De Rostolan) Mapping done | 2021-05-03
THE MASONIC HALL BOARD LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2020-12-31 | 2021-04-26 | 2021-07-31 | 50 | 2021-07-29 | PENDING DOCS |  | 2021-07-22
THREE FINS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG | 2020-12-31 | 2021-06-11 | 2021-08-31 | 110 | 2021-08-31 | WIP | 2 mths extension filed planning audit program. No schedule and supporting docs provided. OSM list sent on 04.08.21. WIP, OSM list sent and meeting with client done on 12.08. Client will provide part by part. Awaiting client to appoint us as auditor and pending substantial information like revenue, salaries and RP. will discuss with client all the outstanding on 24.08. Updated on 22.08. | 2021-08-01
UNIQCASH PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG |  | 2021-02-22 | 2021-04-30 | 20 | 2021-05-31 | FINALIZING | PMFT report obtained. will schedule one day for wrapping up. | 2021-02-22