## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
A&O FARMERS PTE. LTD. |  | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | KWEH CHUN SHENG, LOK YEE RENNIE THEW | 2021-03-31 | 2021-08-16 | 2021-09-30 | 40 | 2021-08-27 | WIP | Queries raised and sent by 19-8-21; Queries replied by Mr Thomas @ 20-8-21 (partial); **Pending the 5Q(queries) replied from Siew Ee | 2021-08-17
CRAVINGS CURATORS SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | ANDY, HSL | TZE KARN KONG | KWEH CHUN SHENG | KWEH CHUN SHENG | 2020-12-31 | 2021-08-16 | 2021-08-31 | 64 | 2021-08-31 | WIP |  | 2021-08-18
CRAVINGS CURATORS SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | KWEH CHUN SHENG | KWEH CHUN SHENG | 2020-12-31 | 2021-08-16 | 2021-09-05 | 16 | 2021-09-05 | YET TO START |  | 2021-08-18
GLOBAL LNC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | KWEH CHUN SHENG | 2021-03-31 | 2021-08-20 | 2021-09-30 | 35 | 2021-08-27 | WIP |  | 2021-08-23
GLOBAL OCEANLINK SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | KWEH CHUN SHENG | KWEH CHUN SHENG | 2020-12-31 | 2021-08-12 | 2021-08-20 | 40 | 2021-08-20 | CLEARING REVIEW POINTS | Pending Clients return confirmations | 2021-08-12
TIGER CONSULTING SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | KWEH CHUN SHENG | KWEH CHUN SHENG | 2020-12-31 | 2021-08-12 | 2021-08-20 | 16 | 2021-08-20 | REVIEWING - PARTNER |  | 2021-08-16