## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
2J HOLDINGS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | JIA XIAN FOONG | 2021-03-31 | 2021-08-16 | 2021-09-30 | 80 | 2021-08-31 | WIP |  | 2021-08-17
A&O FARMERS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | HAO YAN, LOK YEE RENNIE THEW | 2021-03-31 | 2021-08-16 | 2021-09-30 | 40 | 2021-08-27 | WIP | Queries raised and sent by 19-8-21; Queries replied by Mr Thomas @ 20-8-21 (partial); **Pending the 5Q(queries) replied from Siew Ee; Replied by Siew Ee @23-8-21; Will proceed before 1-9-2021 | 2021-08-17
ASIA PACIFIC BIOINFORMATICS NETWORK LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | MUI LING TAN | MUI LING TAN | 2020-12-31 | 2021-05-19 | 2021-06-30 | 40 | 2021-06-16 | PENDING DOCS & PAYMENT |  | 2021-06-07
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG, YING QIN YONG | 2020-12-31 | 2021-01-25 | 2021-04-30 | 40 | 2021-07-31 | PENDING PAYMENT | Send out for adoption: 28 July 2021 | 2021-01-25
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG, YING QIN YONG, JOANNE TEH HUI LING | 2020-12-31 | 2021-03-29 | 2021-04-30 | 80 | 2021-04-16 | SIGNED | Sent for adoption: 28 July 2021 | 2021-03-29
BL PROJECTS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG | 2020-12-31 | 2021-07-02 | 2021-06-30 | 90 | 2021-08-31 | YET TO START | Yet to start. Planning meeting with partner on 18.08. TBC with Ray Kong for the AR filing extension. Updated on 26.08 | 2021-08-02
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | YU XUEN NG | 2019-12-31 | 2020-10-12 | 2020-11-30 | 60 | 2021-03-15 | PENDING DOCS | Pending signing doc. Follow up on 23/8 | 2020-10-29
CONVERSANT GLOBAL PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-08 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | Finalising working paper and draft report | 2021-03-23
CONVERSANT INVESTMENT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | XUN HUI SOH | XUN HUI SOH, SU HUI TAN | 2019-12-31 | 2020-05-22 | 2020-06-30 | 20 | 2021-03-12 | PENDING DOCS | Sent out adoption on 14 Oct Sent for partner review in softcopy on 26 June | 2020-06-05
CONVERSANT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-11 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | Amendment to do | 2021-03-23
CONVERSANT SOLUTIONS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | MUI LING TAN, YU XUEN NG, PIK EN TOH | 2020-12-31 | 2021-03-03 | 2021-06-30 | 100 | 2021-07-31 | SENT OUT FOR ADOPTION | Amendment done on 31 Aug | 2021-03-24
GLOBAL LNC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SHARON WONG, KWEH CHUN SHENG | 2021-03-31 | 2021-08-20 | 2021-09-30 | 35 | 2021-08-27 | WIP |  | 2021-08-23
GLOBAL OCEANLINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, SOO WUEN ONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 140 | 2021-08-31 | WIP | Fieldwork started on 23 August 2021 | 2021-08-02
HDR PAYMENT PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-06-11 | 2021-08-31 | 100 | 2021-09-30 | SENT OUT FOR ADOPTION | Extension filed Audit for 2019 (opening) and 2020 | 2021-08-01
HDR SG PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-06-11 | 2021-08-31 | 8 | 2021-09-30 | SENT OUT FOR ADOPTION | 2 MTHS EXTENSION FILED FIRST SET OF FS | 2021-08-01
HHL CREDIT PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH |  |  |  | 24 | 2021-08-31 | FINALIZING | To print working paper and submit to partner | 2020-08-20
LMB AEROSPACE ASIA PACIFIC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2021-06-30 | 2021-07-06 | 2021-12-31 | 60 | 2021-08-31 | WIP |  | 2021-07-26
LUMIPLAN ASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YING QIN YONG | YING QIN YONG | 2021-03-31 | 2021-06-17 | 2021-09-30 | 60 | 2021-07-30 | WIP |  | 2021-07-23
NOVEL COMMUNICATION PTE. LTD. | SYA PAC | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, KOK YEE CHOONG | 2020-12-31 | 2021-05-07 | 2021-06-30 | 110 | 2021-06-23 | WIP | Fieldwork start on 12.08.21, WIP on 27.08.21, pending query from client, go through the response from client for previous query | 2021-06-10
NUTRIXPERTS PTE. LTD. (FORMERLY KNOWN AS LISA RD SINGAPORE PTE. LTD.) | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-09-03 | 2020-09-30 | 40 | 2021-04-30 | KIV | Client has replied, and said documents are all provided but i was preparing the queries on top of the documents received, will follow up with her again (1 Sep 21) | 2020-09-07
PROCESS TECHNOLOGY CONSULTANTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | WEI QI YU, XUN HUI SOH | 2021-03-31 | 2021-06-09 | 2021-09-30 | 60 | 2021-07-30 | REVIEWING - MANAGER | 1. Account received on 9 June 2021 | 2021-06-25
SUPREME LINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, JIA XIAN FOONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 70 | 2021-08-31 | WIP |  | 2021-08-02
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-11-04 | 2020-11-30 | 70 | 2021-03-31 | PENDING DOCS | All copies signed, pending cor sec document to be received. | 2020-11-23
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | YU XUEN NG, SOO WUEN ONG | 2020-12-31 | 2021-03-09 | 2021-06-30 | 80 | 2021-07-31 | SENT OUT FOR ADOPTION | To sent for adoption with other companies | 2021-03-23
TECHNIDRILL AUSTRALASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | JOANNE TEH HUI LING, CHEA CHEI LOH | 2020-12-31 | 2021-03-29 | 2021-03-29 | 80 | 2021-05-14 | PENDING DOCS | 1. Send out adoption on 30 June 2021 Email d.siervo@altios.com (Donnabelle Siervo) CC g.derostolan@altios.com (Geraldine De Rostolan) Mapping done | 2021-05-03
THE MASONIC HALL BOARD LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2020-12-31 | 2021-04-26 | 2021-07-31 | 50 | 2021-07-29 | WIP |  | 2021-07-22
THREE FINS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG | 2020-12-31 | 2021-06-11 | 2021-08-31 | 110 | 2021-08-31 | REVIEWING - PARTNER | 2 mths extension filed planning audit program. No schedule and supporting docs provided. OSM list sent on 04.08.21. WIP, OSM list sent and meeting with client done on 12.08. Client will provide part by part. Awaiting client to appoint us as auditor and pending substantial information like revenue, salaries and RP. will discuss with client all the outstanding on 24.08. Will pass draft FS to partner for review on 27.08. AWP and audit program need to tidy up. Updated on 26.08. | 2021-08-01
UNIQCASH PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG |  | 2021-02-22 | 2021-04-30 | 20 | 2021-05-31 | FINALIZING | PMFT report obtained. will schedule one day for wrapping up. | 2021-02-22