## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
1PLUS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-05-31 | 2021-06-10 | 2021-11-30 | 24 | 2021-08-20 | SENT OUT FOR ADOPTION | Sent 15/07 | 2021-06-14
1PLUS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-05-31 | 2021-06-10 | 2022-11-30 | 12 | 2021-08-20 | SENT OUT FOR ADOPTION |  | 2021-06-14
88 GARAGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 |  | 2021-06-30 | 24 | 2021-07-16 | KIV | Pending Dec 2020 bank statement from client | 2021-06-08
88 GARAGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 8 | 2021-07-16 | WIP |  | 2021-06-08
ACE RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-07-14 | 2021-12-31 | 32 | 2021-08-27 | REVIEWING - MANAGER | Include yearly accounting - sent draft accounts & ECI to clients for approval | 2021-07-19
ACE RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-07-14 | 2022-11-30 | 8 | 2021-08-27 | REVIEWING - MANAGER | ECI due 26/9/21 | 2021-07-19
AIMTECH SYSTEMS PTE LTD | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 | 2021-07-15 |  | 15 | 2021-08-06 | SENT OUT FOR ADOPTION | Sent to Karn Lee (23/08) | 2021-07-19
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-07-26 | 2021-11-30 | 24 | 2021-08-20 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
ALUMINIUM & TECHNOLOGIES (ALTECH) PTE LTD | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2019-03-31 |  | 2020-11-30 | 8 | 2020-11-06 | KIV | LATE FILING - Compilation FS & income tax computation Client will send us account by 31.7.2020. (last follow up email with Steven dd 22.7.2020) | 2020-04-01
APPRAISAL VP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-03-01 | 2021-06-30 | 24 | 2021-04-02 | PENDING PAYMENT | Include yearly acctg | 2021-03-11
APPRAISAL VP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-03-01 | 2021-11-30 | 12 | 2021-04-02 | PENDING PAYMENT | ECI due 26/3/21 | 2021-03-11
AR CREDITZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-05 | INTERIM COMPLETED | Include accounting. ECI due 26/3/21 | 2021-01-11
ASIAN GOLF INDUSTRY FEDERATION | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-06-30 | 2021-01-04 | 2021-04-15 | 12 | 2021-02-26 | PENDING PAYMENT |  | 2021-01-05
ASSURANCE CONSULTANCY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-05-31 | 2021-07-07 | 2021-11-30 | 24 | 2021-08-06 | PENDING PAYMENT | Sent (06/08) | 2021-07-19
ASSURANCE CONSULTANCY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-05-31 | 2021-07-07 | 2022-11-30 | 12 | 2021-08-06 | PENDING PAYMENT | ECI (11/08), sent (06/08) | 2021-07-19
AUTOCOUNT (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 16 | 2021-08-27 | PENDING DOCS & PAYMENT | ECI due 26/3/21 | 2021-03-15
AUTOMOTION ENGINEERING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-05-31 |  | 2021-11-30 | 6 | 2020-12-25 | INTERIM COMPLETED |  | 2020-06-22
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-19 | PENDING DOCS & PAYMENT | Include accounting. ECI submitted 19/02, audited report (13/08), sent (18/08) | 2021-01-11
BENZ RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-03-31 | 2021-06-10 | 2021-09-30 | 24 | 2021-08-13 | SENT OUT FOR ADOPTION | Queries sent 12/07 | 2021-06-14
BENZ RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-03-31 | 2021-06-10 | 2022-11-30 | 12 | 2021-08-13 | SENT OUT FOR ADOPTION |  | 2021-06-14
BIG IMAGE GROUP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-06-30 |  | 2020-12-31 | 16 | 2021-04-09 | ACCOUNT NOT IN |  | 2020-07-20
BIG IMAGE GROUP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-06-30 |  | 2021-11-30 | 6 | 2021-04-09 | ACCOUNT NOT IN |  | 2020-07-20
BLUELAMBDA PRIVATE LIMITED | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-06-30 |  | 2021-11-30 | 8 | 2021-02-19 | INTERIM COMPLETED | ECI filed 31/8/20 | 2020-07-13
BTB CREDITZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-09-10 | PENDING DOCS | Include accounting. ECI due 26/3/21 | 2021-01-11
BUGIS CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-02-19 | SENT OUT FOR ADOPTION | Include accounting. ECI due 26/3/21 | 2021-01-11
CANNY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEA CHEI LOH | 2020-02-29 |  | 2020-06-14 | 16 | 2020-08-08 | PENDING PAYMENT | PENDING SECRETARY DOCS | 2020-04-06
CAPITAL C PEOPLE XPERIENCE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YEE TING GWEE | TZE KARN KONG | SALLY | 2019-12-31 |  | 2020-06-30 | 6 | 2020-11-13 | PENDING PAYMENT | XBRL (FULL), sent 20/11 | 2020-07-30
CAPITALL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YEE TING GWEE | TZE KARN KONG | CHEA CHEI LOH | 2019-12-31 | 2020-11-06 | 2020-06-30 | 4 | 2020-11-13 | PENDING PAYMENT | XBRL (FULL) Audit only half way (check with Yong Lai dd 25.6.2020) | 2020-04-02
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-07-30 | KIV | Pending e-file tax YA2021 | 2021-01-11
CASHMAX CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-12 | SENT OUT FOR ADOPTION | Include accounting. ECI due 26/3/21 | 2021-01-11
CRAFTWERKZ INTERIOR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | GST REGISTRATION APPLICATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2021-04-30 |  | 2020-10-09 | 8 | 2020-11-27 | KIV | Client request to apply GST by end of November | 2020-10-01
CRAWFORT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YEE TING GWEE | TZE KARN KONG | CHEW WEI HNG | 2019-12-31 |  | 2020-06-30 | 4 | 2020-10-09 | PENDING PAYMENT | XBRL (FULL) Victoria will start planning until 6 July (check with Victoria dd 25.6.2020) | 2020-04-02
CRAWFORT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-08-13 | 2021-11-30 | 24 | 2021-09-10 | YET TO START | Include accounting. ECI due 26/3/21 | 2021-01-11
CRE8IOT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | HUI LING PANG | 2021-07-31 | 2021-08-30 | 2022-01-31 | 24 | 2021-09-17 | YET TO START |  | 2021-08-30
CRE8IOT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | HUI LING PANG | 2021-07-31 | 2021-08-30 | 2022-11-30 | 10 | 2021-09-17 | YET TO START | ECI due 26/10/2021 | 2021-08-30
CREDIT 89 (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-01-29 | PENDING DOCS | Include accounting. ECI due 26/3/21 | 2021-01-11
DRS. AUDREY & ALEXANDER PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YEE TING GWEE | YEE TING GWEE | 2020-12-31 |  | 2021-06-30 | 24 | 2021-05-28 | PENDING PAYMENT |  | 2021-03-01
DRS. AUDREY & ALEXANDER PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YEE TING GWEE | YEE TING GWEE | 2020-12-31 |  | 2021-11-30 | 16 | 2021-05-28 | PENDING PAYMENT |  | 2021-03-01
DUSCHE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | GST SUBMISSION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | YI LING CHOO | 2021-02-28 |  | 2020-09-30 | 16 | 2020-09-30 | PENDING PAYMENT | GST submission for 01-06-2020 to 31-08-2020 | 2020-09-01
EC WEB PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2021-04-30 | 2021-05-11 | 2022-11-30 | 8 | 2021-06-25 | SENT OUT FOR ADOPTION | ECI due 26/7/21 | 2021-05-12
ECO FLOORING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2021-05-31 | 2021-08-04 | 2021-11-30 | 24 | 2021-08-27 | WIP |  | 2021-08-09
ECO FLOORING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2021-05-31 | 2021-08-04 | 2022-11-30 | 12 | 2021-08-27 | WIP | ECI due 26/8/21 | 2021-08-09
EDG DESIGN - ASIA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2019-12-31 |  | 2020-11-30 | 6 | 2021-08-27 | ACCOUNT NOT IN | Pending audited report, checked with Hwee Xin on 10/5/2021 | 2020-04-02
EDG DESIGN - ASIA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2019-12-31 |  | 2020-08-29 | 4 | 2021-08-27 | ACCOUNT NOT IN | XBRL (FULL) | 2020-04-02
EMVERTEX CAPITAL | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-04-15 | 16 | 2021-04-16 | PENDING DOCS & PAYMENT | INCOME TAX COMPUTATION & 4-LINE STATEMENTS (YA2021) | 2021-01-06
EMVERTEX CREDIT (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-08-27 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
ESHWAR CAPITAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 | 2021-07-21 | 2022-11-30 | 8 | 2021-09-10 | PENDING DOCS & PAYMENT | ECI due 26/9/21, sent 15/09 | 2021-07-26
ESHWAR CAPITAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 | 2021-07-21 | 2021-12-31 | 24 | 2021-09-10 | PENDING DOCS & PAYMENT | Include yearly accounting, sent 15/09 | 2021-07-26
EVERLUMIERE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LEE MIN TEO | 2020-12-31 | 2021-03-16 | 2021-06-30 | 24 | 2021-05-07 | PENDING PAYMENT |  | 2021-03-16
FAST MONEY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-08-16 | 2021-11-30 | 24 | 2021-08-20 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
FAST RECOVERY (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-08-16 | 2021-11-30 | 24 | 2021-08-20 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
FAST RECOVERY (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-06-30 | 24 | 2021-02-26 | INTERIM COMPLETED |  | 2021-01-11
FAST WERKZ GARAGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-06-30 | 16 | 2021-03-19 | PENDING DOCS |  | 2021-01-04
FAST WERKZ GARAGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-06-30 | 10 | 2021-03-19 | PENDING DOCS | To file ECI by 26/3/21 | 2021-01-04
FAST WERKZ GARAGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2021-07-31 |  | 2021-08-31 | 12 | 2021-08-13 | SENT OUT FOR ADOPTION | ZEROING ACCOUNTS AND FINAL TAX SUBMISSION FOR YA2022 | 2021-07-26
FORTUNE CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-02-26 | INTERIM COMPLETED | Include accounting. ECI due 26/3/21 | 2021-01-11
FOX STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-06-30 | 24 | 2021-06-04 | PENDING PAYMENT |  | 2021-05-05
FOX STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 8 | 2021-06-04 | KIV | Pending e-filed YA2021 | 2021-05-05
GAIN CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-02-19 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
GLAM CONSULTANCY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2021-06-30 | 2021-07-14 | 2021-12-31 | 32 | 2021-08-27 | REVIEWING - TEAM LEAD | Include yearly accounting - sent draft accounts & ECI to clients for approval | 2021-07-19
GLAM CONSULTANCY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2021-06-30 | 2021-07-14 | 2022-11-30 | 8 | 2021-08-27 | REVIEWING - TEAM LEAD | ECI due 26/9/21 | 2021-07-19
GM CREDITZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-08-13 | 2021-11-30 | 24 | 2021-08-27 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
GOAL ARENA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-12-31 | 2021-02-22 | 2021-11-30 | 8 | 2021-04-16 | INTERIM COMPLETED |  | 2021-04-01
GOLDEN MILE BISTRO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-07-27 | 2021-06-30 | 16 | 2021-08-20 | PENDING DOCS | Yearly accounting (P&L and B/S only) | 2021-08-02
GOLDEN MILE BISTRO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-07-27 | 2021-11-30 | 12 | 2021-08-20 | PENDING DOCS |  | 2021-08-02
GOLDERTEK PETROLEUM AND CHEMICALS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | TAT WAI DAVID LEE | 2020-12-31 | 2021-03-26 | 2021-06-30 | 16 | 2021-05-07 | SENT OUT FOR ADOPTION |  | 2021-03-30
GOSFORD LEATHER TRIM (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-03-25 | 2021-06-30 | 16 | 2021-07-23 | PENDING DOCS & PAYMENT | Pending client docs (M'sia MCO til 28.6.2021) Documents requested dd 1.6.2021 | 2021-03-30
GOSFORD LEATHER TRIM (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-03-25 | 2021-11-30 | 12 | 2021-07-23 | SENT OUT FOR ADOPTION | Pending client docs (M'sia MCO til 28.6.2021) Documents requested dd 1.6.2021 | 2021-03-30
GT CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEA CHEI LOH | 2019-12-31 |  | 2020-11-30 | 6 | 2020-10-23 | PENDING PAYMENT | Pending audited report (Followup with Jacinth on 11/5) | 2020-04-02
GT CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-26 | INTERIM COMPLETED | Include accounting. ECI due 26/3/21 | 2021-01-11
GUMMY EDUCATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-03-31 |  | 2020-09-14 | 32 | 2020-05-15 | PENDING PAYMENT | FOLLOW UP, CLIENT SAID WILL RETURN IN AUG 2020 | 2020-04-06
HANSA KK PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | GST REGISTRATION APPLICATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2022-04-30 |  | 2021-07-31 | 24 | 2021-05-28 | PENDING PAYMENT | The property acquisition is schedule for completion not later then 21/7/2021 | 2021-05-24
HAPPY CASH PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-12 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
HEALTH CAPITAL (PUNGGOL OASIS) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2021-01-31 | 2021-02-23 | 2021-11-30 | 12 | 2021-04-02 | KIV | Pending E-file YA2022 | 2021-02-23
HEALTH CAPITAL II PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2021-04-30 | 2021-05-11 | 2021-10-31 | 32 | 2021-05-28 | PENDING DOCS & PAYMENT |  | 2021-05-11
HEALTH CAPITAL II PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2021-04-30 | 2021-05-11 | 2022-11-30 | 16 | 2021-05-28 | PENDING DOCS & PAYMENT | ECI due 26/7/21 | 2021-05-11
HHL CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-08-27 | PENDING PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
HOUGANG 678 EATING HOUSE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 | 2021-08-11 | 2021-12-31 | 32 | 2021-09-10 | WIP | Include yearly accounting | 2021-08-16
HOUGANG 678 EATING HOUSE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 | 2021-08-11 | 2022-11-30 | 8 | 2021-09-10 | WIP | ECI due 26/9/2021 | 2021-08-16
HUACHUANG SINGAPORE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2021-06-30 | 2021-08-23 | 2021-12-31 | 24 | 2021-09-10 | PENDING DOCS & PAYMENT | Include yearly accounting | 2021-08-23
HUACHUANG SINGAPORE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2021-06-30 | 2021-08-23 | 2022-11-30 | 12 | 2021-09-10 | PENDING DOCS & PAYMENT |  | 2021-08-23
HUP HOE CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 | 2021-06-24 | 2021-11-30 | 24 | 2021-09-10 | WIP | Include accounting. ECI (26/03), audited report (25/06) | 2021-01-11
I3 ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-11-30 | 2021-07-05 | 2021-05-31 | 24 | 2021-07-30 | SENT OUT FOR ADOPTION | Sent 14/07 | 2021-07-12
I3 ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-11-30 | 2021-07-05 | 2021-11-30 | 8 | 2021-07-30 | SENT OUT FOR ADOPTION | Sent 14/07 | 2021-07-12
ICHILD COMPANY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-08-31 |  | 2021-11-30 | 12 | 2020-12-18 | KIV | Pending e-filed YA2021 | 2020-11-02
ICOM ENGINEERING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-03-25 | 2021-06-30 | 10 | 2021-05-07 | PENDING DOCS & PAYMENT |  | 2021-04-15
IEXPORTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2019-03-31 |  | 2019-09-30 | 20 | 2020-12-11 | PENDING DOCS & PAYMENT | INCLUDE YEARLY ACCTG REQUESTED FOR ACCOUNT, CLIENT SENT YEAR 2020 ACC, STILL PENDING YEAR 2019 ACC LAST FOLLOW UP 4/8/2020, CLIENT SAID WILL SEND DOCS TO OFFICE | 2020-07-06
IEXPORTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2019-03-31 |  | 2020-11-30 | 4 | 2020-12-11 | PENDING DOCS & PAYMENT |  | 2020-07-06
INFORMA SOLUTIONS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-07-31 | 2021-06-09 | 2021-01-31 | 32 | 2021-09-24 | ACCOUNT NOT IN | CLIENT HAVENT FINALISED THE MANAGEMENT ACCOUNTS, FILE AR FIRST | 2020-08-24
INFORMA SOLUTIONS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-07-31 | 2021-06-09 | 2021-11-30 | 8 | 2021-09-24 | ACCOUNT NOT IN | ECI due 26/10/2020 | 2020-08-24
IOVA CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-05-06 | 2021-06-30 | 16 | 2021-05-21 | PENDING DOCS & PAYMENT |  | 2021-05-06
IOVA CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-05-06 | 2021-11-30 | 8 | 2021-05-21 | PENDING DOCS & PAYMENT |  | 2021-05-06
IZAKAYA 95 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-06-30 | 2021-08-02 | 2021-12-31 | 24 | 2021-09-10 | YET TO START |  | 2021-08-02
IZAKAYA 95 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-06-30 | 2021-08-02 | 2022-11-30 | 12 | 2021-09-10 | YET TO START | ECI due 26/9/21 | 2021-08-02
J. HANG INVESTMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2021-03-31 |  | 2021-06-30 | 20 | 2021-05-14 | SENT OUT FOR ADOPTION |  | 2021-04-22
JEFFLEE CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 16 | 2021-08-27 | INTERIM COMPLETED |  | 2021-05-03
JLT ION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | GST REGISTRATION APPLICATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | TEE PEI CHING | 2021-12-31 | 2021-08-30 | 2021-09-10 | 10 | 2021-09-10 | SENT OUT FOR ADOPTION |  | 2021-08-30
JLT SG PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-12-31 |  | 2021-06-30 | 8 | 2021-07-09 | PENDING PAYMENT | XBRL (FULL SET) | 2021-06-30
JNB CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-02-26 | SENT OUT FOR ADOPTION | Include accounting. ECI due 26/3/21 | 2021-01-11
JNB CREDITZ | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-12-31 | 2021-03-25 | 2021-04-15 | 16 | 2021-04-09 | PENDING DOCS | INCOME TAX COMPUTATION & 4-LINE STATEMENTS (YA2021) | 2021-01-06
JSMY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-06-30 | 2020-12-29 | 2020-12-31 | 24 | 2021-04-30 | PENDING PAYMENT | Yearly accounting, sent 03/05 | 2020-11-03
JSMY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-06-30 | 2020-12-29 | 2020-12-31 | 10 | 2021-04-30 | PENDING PAYMENT | sent 03/05 | 2020-11-03
JSMY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-06-30 | 2020-12-29 | 2021-11-30 | 8 | 2021-04-30 | PENDING PAYMENT | sent 03/05 | 2020-11-03
KAIIRON PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-26 | INTERIM COMPLETED | Include accounting. ECI (25/03), audited report (29/07) | 2021-01-11
KAIROS MILLENIUM RESOURCES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-06-30 | 2021-07-27 | 2021-11-30 | 8 | 2021-09-03 | WIP |  | 2021-07-27
KAZHOU PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 |  | 2021-06-30 | 32 | 2021-06-25 | PENDING PAYMENT |  | 2021-03-15
KAZHOU PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 |  | 2021-11-30 | 12 | 2021-06-25 | PENDING PAYMENT | ECI (25/03) | 2021-03-15
LANDART DESIGN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-01-31 | 2021-06-18 | 2022-11-30 | 8 | 2021-08-06 | PENDING PAYMENT | Sent (06/08) | 2021-06-21
LE DESIGN STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-10-31 |  | 2021-04-30 | 36 | 2021-05-21 | ACCOUNT NOT IN |  | 2020-11-02
LE DESIGN STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-10-31 |  | 2021-04-30 | 12 | 2021-05-21 | ACCOUNT NOT IN |  | 2020-11-02
LE DESIGN STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-10-31 |  | 2021-11-30 | 10 | 2021-05-21 | ACCOUNT NOT IN |  | 2020-11-02
LE PLUMBING & CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-04-30 |  | 2020-10-31 | 16 | 2021-03-26 | ACCOUNT NOT IN | Account not ready, last follow up with Grace on 26/5 | 2020-04-22
LE PLUMBING & CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-04-30 |  | 2020-10-31 | 8 | 2021-03-26 | ACCOUNT NOT IN | Account not ready, last follow up with Grace on 26/5 | 2020-04-22
LE PLUMBING & CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-04-30 |  | 2021-11-30 | 6 | 2021-03-26 | ACCOUNT NOT IN | Account not ready, last follow up with Grace on 26/5 | 2020-04-22
LEE HUAT HOLDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 | 2021-08-11 | 2021-12-31 | 32 | 2021-09-17 | PENDING DOCS & PAYMENT | Include yearly accounting, sent 07/09 | 2021-08-16
LEE HUAT HOLDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 | 2021-08-11 | 2022-11-30 | 8 | 2021-09-17 | PENDING DOCS & PAYMENT | ECI due 26/9/2021, sent 07/09 | 2021-08-16
LEONG JI SEAFOOD PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 | 2021-05-15 | 2021-06-30 | 24 | 2021-07-23 | WIP | Queries sent 16/06, client never response to email and phone | 2021-05-17
LEONG JI SEAFOOD PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 | 2021-05-15 | 2021-06-30 | 8 | 2021-07-23 | WIP | Client never response to email and phone | 2021-05-17
MAGNUS CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 |  | 2021-11-30 | 24 | 2021-03-05 | PENDING DOCS & PAYMENT | Include accounting. ECI (19/03), audited report (16/07), sent (06/08) | 2021-01-11
MARIO SOTINA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-08-31 | 2021-01-06 | 2021-02-28 | 16 | 2021-06-25 | PENDING PAYMENT |  | 2020-09-28
MARIO SOTINA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-08-31 | 2021-01-06 | 2021-11-30 | 8 | 2021-06-25 | PENDING PAYMENT | ECI filed 30/11 | 2020-09-28
MAX CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-12-31 | 2021-08-13 | 2021-11-30 | 24 | 2021-09-03 | REVIEWING - TEAM LEAD | Include accounting. ECI due 26/3/21 | 2021-01-11
MOBILER STAR (ORCHARD) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-02-29 | 2020-06-16 | 2020-08-31 | 6 | 2020-11-27 | KIV | Pending E-file tax YA2021 | 2020-06-22
MOBILER STAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | LI FANG ANGELA CHAI | 2020-12-31 | 2021-07-07 | 2021-06-30 | 24 | 2021-08-27 | YET TO START | Include yearly accounting | 2021-07-12
MOBILER STAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | LI FANG ANGELA CHAI | 2020-12-31 | 2021-07-07 | 2021-11-30 | 12 | 2021-08-27 | YET TO START | incomplete information - pending for docs | 2021-07-12
MUJIANG DESIGN WORKSHOP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2021-02-28 | 2021-03-23 | 2021-06-30 | 12 | 2021-05-07 | PENDING PAYMENT | Final tax computation (YA2021 & YA2022) for striking off | 2021-03-29
NEW ERA CREDIT (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-12-31 | 2021-07-23 | 2021-11-30 | 24 | 2021-07-30 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
NOVEL COMMUNICATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YEE TING GWEE | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-09-24 | INTERIM COMPLETED | ECI due 26/3/21 | 2021-03-10
OCEAN ENTERPRISE (INT) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2019-03-31 |  | 2020-11-30 | 20 | 2020-11-06 | KIV | Sent deadline reminder dd 26.5.2020 Last status dd 4.6.2020, client need to amend the million account as found out there is term loan dd 17.5.2017 omitted to key into system Client need more time to update account and call bank to request term loan statement year 2017 (last follow date 14.7.2020) Send whatsapp reminder dated 3.11.2020 | 2020-04-02
OCEAN ENTERPRISE (INT) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-03-31 |  | 2020-09-30 | 24 | 2020-11-06 | ACCOUNT NOT IN | Compilation FS & income tax computation | 2020-04-06
ONE DESIRE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-05-06 | 2021-06-30 | 24 | 2021-06-25 | PENDING DOCS & PAYMENT |  | 2021-05-06
ONE DESIRE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-05-06 | 2021-11-30 | 8 | 2021-06-25 | PENDING DOCS & PAYMENT |  | 2021-05-06
ONLINE STORE NINJAS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-06-30 |  | 2021-11-30 | 8 | 2021-01-15 | INTERIM COMPLETED | ECI filed on 25/8/20 | 2020-07-20
PING TAN CHAMBER OF COMMERCE (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YEE TING GWEE | YEE TING GWEE | 2020-12-31 | 2021-03-08 | 2021-06-30 | 8 | 2021-03-12 | PENDING DOCS | Zeroing accts and tax submission for YA2021 | 2021-03-08
PLAYTRENDS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-03-31 | 2020-08-05 | 2020-09-30 | 24 | 2021-04-02 | PENDING DOCS & PAYMENT | REVIEW DONE, CHECKING WITH CLIENT IF HAVE REMAINING MONTHS BANK STATEMENTS | 2021-03-08
PLAYTRENDS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-03-31 | 2020-08-05 | 2021-11-30 | 12 | 2021-04-02 | PENDING DOCS & PAYMENT |  | 2021-03-08
POSH RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-03-31 | 2021-06-10 | 2021-09-30 | 24 | 2021-08-13 | SENT OUT FOR ADOPTION | Queries sent 12/07 | 2021-06-14
POSH RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-03-31 | 2021-06-10 | 2022-11-30 | 12 | 2021-08-13 | SENT OUT FOR ADOPTION |  | 2021-06-14
POWER CREDIT | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-04-15 | 16 | 2021-04-02 | PENDING PAYMENT | INCOME TAX COMPUTATION & 4-LINE STATEMENTS AND SUBMISSION OF PERSONAL TAX (YA2021) | 2021-01-06
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | YI LING CHOO | 2019-12-31 |  | 2020-11-30 | 16 | 2020-07-10 | SENT OUT FOR ADOPTION | Pending audited report | 2020-04-02
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-04-30 | REVIEWING - TEAM LEAD | Include accounting. ECI due 26/3/21 | 2021-01-11
PT DESIGN STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-04-12 | 2021-06-30 | 24 | 2021-05-14 | PENDING PAYMENT | send queries dd 11.5.2021 | 2021-04-12
PT DESIGN STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-04-12 | 2021-06-30 | 4 | 2021-05-14 | PENDING PAYMENT | Emailed Ray to review dd 9.6.2021 | 2021-04-12
PT DESIGN STUDIO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-04-12 | 2021-11-30 | 8 | 2021-05-14 | KIV | Pending E-file tax YA2021 | 2021-04-12
PT-G BUILDERS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YEE TING GWEE | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 32 | 2021-10-29 | INTERIM COMPLETED | ECI due 26/3/21 | 2021-03-08
QHFOXX PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 |  | 2021-06-30 | 32 | 2021-05-28 | PENDING PAYMENT |  | 2021-03-15
QHFOXX PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-12-31 |  | 2021-11-30 | 12 | 2021-07-02 | PENDING PAYMENT | ECI (25/03), Sent (28/06) | 2021-03-15
QING HENG INVESTMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YONG KEAN LOOI | SALLY | 2021-03-31 |  | 2021-09-30 | 24 | 2021-06-11 | PENDING DOCS & PAYMENT | Approved management account 31/05 | 2021-05-03
QING HENG INVESTMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YONG KEAN LOOI | SALLY | 2021-03-31 |  | 2022-11-30 | 8 | 2021-06-11 | PENDING DOCS & PAYMENT | Approved management account 31/05 | 2021-05-03
RAFFLES CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-07-30 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
RECOVERY 88 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2019-12-31 |  | 2020-06-14 | 24 | 2020-04-24 | PENDING PAYMENT | PENDING payment | 2020-04-06
RM CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-06-18 | PENDING PAYMENT | Filed ECI YA 2021 | 2021-01-11
RSS TECHNOLOGY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2021-06-30 |  | 2021-12-31 | 24 | 2021-10-01 | ACCOUNT NOT IN |  | 2021-09-16
RSS TECHNOLOGY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2021-06-30 |  | 2022-11-30 | 8 | 2021-10-01 | ACCOUNT NOT IN | ECI due 26/9/2021 | 2021-09-16
SAL SHIPPING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 | 2021-03-24 | 2021-06-30 | 16 | 2021-05-14 | PENDING DOCS & PAYMENT |  | 2021-04-05
SAS CONSULTANTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YEE TING GWEE | TZE KARN KONG | SALLY | 2020-05-31 |  | 2020-11-30 | 32 | 2020-12-25 | WIP |  | 2020-06-29
SAS CONSULTANTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | TZE KARN KONG | SALLY | 2020-05-31 |  | 2020-11-30 | 8 | 2020-12-25 | WIP |  | 2020-06-29
SAS CONSULTANTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | TZE KARN KONG | SALLY | 2020-05-31 |  | 2021-11-30 | 6 | 2020-12-25 | WIP | ECI filed 24/08 | 2020-06-29
SASSAX PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 |  | 2021-12-31 | 32 | 2021-09-10 | WIP | INCLUDING ACCOUNTING, pending some clarification from Paul | 2021-07-05
SASSAX PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2021-06-30 |  | 2022-11-30 | 12 | 2021-09-10 | YET TO START | ECI due 26/9/2021 | 2021-07-05
SDMB TRADE PRIVATE LIMITED | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-06-23 | 2021-06-30 | 24 | 2021-07-09 | PENDING DOCS & PAYMENT |  | 2021-06-23
SDMB TRADE PRIVATE LIMITED | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | CHEW WEI HNG | CHEW WEI HNG | 2020-12-31 | 2021-06-23 | 2021-11-30 | 12 | 2021-07-09 | PENDING DOCS & PAYMENT |  | 2021-06-23
SEA STAR INTERNATIONAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-08-31 |  | 2021-02-28 | 16 | 2021-03-19 | PENDING DOCS & PAYMENT | Signed document is at KL office. | 2020-09-28
SEA STAR INTERNATIONAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | LI FANG ANGELA CHAI | 2020-08-31 |  | 2021-11-30 | 6 | 2021-03-19 | PENDING DOCS & PAYMENT | Signed document is at KL office. | 2020-09-28
SENJA TECHNOLOGIES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-07-31 | 2020-12-16 | 2021-11-30 | 8 | 2021-09-24 | SENT OUT FOR ADOPTION | Sent (20/08) | 2020-12-16
SGP CREDIT SINGAPORE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 24 | 2021-07-30 | PENDING DOCS & PAYMENT | Include accounting. ECI due 26/3/21 | 2021-01-11
SHANMUGAN MONEYLENDER PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 |  | 2021-11-30 | 24 | 2021-07-23 | PENDING PAYMENT | ECI submitted 20/01, audited report received (10/06), sent 22/07 | 2021-01-11
SHINE TRUST TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-02-28 | 2021-03-10 | 2021-08-31 | 24 | 2021-07-02 | PENDING DOCS | Sent 15/09 | 2021-03-11
SHINE TRUST TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2021-02-28 | 2021-03-10 | 2022-11-30 | 24 | 2021-07-02 | PENDING DOCS | Sent 15/09 | 2021-03-11
SIGHAPPI ACHI MONEYLENDER (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 |  | 2021-11-30 | 24 | 2021-02-19 | PENDING DOCS & PAYMENT | ECI submitted 19/01, audited report (26/07), sent (30/07) | 2021-01-11
SIGLAP CLINIC PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-12-31 | 2021-03-12 | 2021-11-30 | 8 | 2021-04-16 | PENDING PAYMENT | ECI due 26/3/21 | 2021-03-11
SILVER TREE INVESTMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2021-05-31 | 2021-07-26 | 2021-11-30 | 24 | 2021-08-27 | PENDING DOCS & PAYMENT |  | 2021-06-15
SILVER TREE INVESTMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2021-05-31 | 2021-07-26 | 2022-11-30 | 12 | 2021-08-27 | PENDING DOCS & PAYMENT |  | 2021-06-15
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 |  | 2021-11-30 | 24 | 2021-08-06 | PENDING DOCS & PAYMENT | ECI submitted 21/01, audited report (07/07), sent (11/08) | 2021-01-11
SIVREN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2019-02-28 |  | 2020-11-30 | 8 | 2020-11-06 | SENT OUT FOR ADOPTION | AR already filed on 26/9/2019; Corporate tax due 30/11/20 Send email reminder dated 3.11.2020 | 2020-04-06
SIVREN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-02-29 |  | 2020-06-14 | 16 | 2020-11-30 | ACCOUNT NOT IN | Compilation FS & income tax computation send email to client follow up account dd 27.4.2020 (last follow up dd 21.5.2020) Client will update us (last follow up dd 25.6.2020) | 2020-04-06
SKILL TRAIN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 | 2021-08-27 | 2021-06-30 | 16 | 2021-09-03 | PENDING DOCS & PAYMENT |  | 2021-08-30
SKILL TRAIN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 | 2021-08-27 | 2021-11-30 | 8 | 2021-09-03 | PENDING DOCS & PAYMENT |  | 2021-08-30
SUPREME HOUZZ DESIGN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | CHEW WEI HNG | 2021-06-30 | 2021-08-04 | 2021-12-31 | 24 | 2021-08-27 | REVIEWING - TEAM LEAD |  | 2021-08-09
SUPREME HOUZZ DESIGN PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | CHEW WEI HNG | 2021-06-30 | 2021-08-04 | 2022-11-30 | 8 | 2021-08-27 | REVIEWING - TEAM LEAD |  | 2021-08-09
SWIFT CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-11-30 | 24 | 2021-02-19 | INTERIM COMPLETED | Include accounting. ECI due 26/3/21 | 2021-01-11
T B C TRANSPORTATION & TRADING PTE LTD | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2019-12-31 | 2021-03-30 | 2021-04-14 | 40 | 2021-04-09 | PENDING DOCS & PAYMENT |  | 2021-03-30
TEJSTAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 | 2021-06-16 | 2021-06-30 | 24 | 2021-06-25 | PENDING DOCS & PAYMENT | Sent (28/06) | 2021-06-21
TEJSTAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 | 2021-06-16 | 2021-06-30 | 12 | 2021-06-25 | PENDING DOCS & PAYMENT | Sent (28/06) | 2021-06-21
TET ASIA SOLUTIONS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 |  | 2021-06-30 | 20 | 2021-05-14 | SENT OUT FOR ADOPTION |  | 2021-04-22
THREE SIXTY-NINE DEVELOPMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-06-30 |  | 2021-11-30 | 8 | 2021-06-25 | YET TO START | ECI filed 17/9/2020, PENDING AUDITED REPORT | 2020-07-20
TRI OCEAN OFFSHORE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 | 2021-03-16 | 2021-06-30 | 32 | 2021-05-07 | SENT OUT FOR ADOPTION |  | 2021-03-16
UNILINK CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2020-12-31 | 2021-08-13 | 2021-11-30 | 16 | 2021-08-27 | SENT OUT FOR ADOPTION |  | 2021-05-03
UNISPIRE CONSULTANCY SERVICES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2021-05-31 | 2021-07-16 | 2021-11-30 | 24 | 2021-08-20 | PENDING DOCS & PAYMENT | Sent account for approval | 2021-07-21
UNISPIRE CONSULTANCY SERVICES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | CHEW WEI HNG | 2021-05-31 | 2021-07-16 | 2022-11-30 | 8 | 2021-08-20 | PENDING DOCS & PAYMENT |  | 2021-07-21
UTILITY (GLO) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | SALLY | 2020-02-29 |  | 2020-06-14 | 10 | 2020-06-19 | ACCOUNT NOT IN | Yearly acctg and income tax computation (client not response to emails and whatsapp call, Mr. Looi said to ignore) | 2020-04-06
UTILITY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-08-31 | 2021-04-01 | 2021-02-28 | 24 | 2021-05-14 | WIP | Followed up on 19/7. Still pending for queries | 2021-04-05
UTILITY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | LI FANG ANGELA CHAI | LI FANG ANGELA CHAI | 2020-08-31 | 2021-04-01 | 2021-11-30 | 10 | 2021-05-14 | WIP |  | 2021-04-05
WECOM TECH & MARKETING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 | 2021-02-25 | 2021-06-30 | 16 | 2021-04-30 | PENDING PAYMENT |  | 2021-02-15
WECOM TECH & MARKETING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | SALLY | 2020-12-31 | 2021-02-25 | 2021-11-30 | 8 | 2021-04-30 | PENDING PAYMENT |  | 2021-02-15
XUAN-U INTERIOR CONSTRUCTION & ENGINEERING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-05-14 | 2021-06-30 | 20 | 2021-07-23 | SENT OUT FOR ADOPTION |  | 2021-06-07
YU YANG CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-02-25 | 2021-06-30 | 24 | 2021-05-07 | PENDING PAYMENT |  | 2021-04-12
YU YANG CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | POH YEN LWI | POH YEN LWI | 2020-12-31 | 2021-02-25 | 2021-11-30 | 8 | 2021-05-07 | KIV | Pending E-file tax YA2021 | 2021-04-12
ZHANG HONG CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | LEE MIN TEO | 2020-12-31 | 2021-03-26 | 2021-06-30 | 16 | 2021-04-30 | PENDING PAYMENT |  | 2021-04-05
ZHANG HONG CONSTRUCTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | SALLY | LEE MIN TEO | 2020-12-31 | 2021-03-26 | 2021-11-30 | 8 | 2021-04-30 | PENDING PAYMENT |  | 2021-04-05