## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
1 2 LEND PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
1 2 LEND PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-18 | ACCOUNT NOT IN | Roll forward AWP and audit programme | 2021-09-13
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-11 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-08
365 CREDIT SOLUTIONS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, SHARON WONG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | EMILY TO UPDATE REVENUE AND TOC AWP BASED ON THE 50 CONTRACTS - SOO WUEN WILL PROVIDE GUIDANCE | 2021-09-01
365 CREDIT SOLUTIONS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2022-04-30 | 20 | 2021-10-31 | WIP | Softcopies of loan contract received, to inform Emily | 2021-09-20
ADVANCE CASH CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | HWEE XIN LIM | KOK YEE CHOONG | EMILY GOH, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-20 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program - In progress | 2021-09-14
ANDAL ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
ANDAL ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
AR CREDITZ PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | YU XUEN NG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
AR CREDITZ PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | YU XUEN NG | KWEH CHUN SHENG, EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-01
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-22 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-15
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-04 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) - samples sent in, Emily is performing vouching | 2021-09-28
BUGIS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | PAI NEE WONG | YU XUEN NG | EMILY GOH, YONG LAM NG | 2021-12-31 | 2021-09-14 | 2021-12-31 | 20 | 2021-10-31 | PLANNING COMPLETED - WITH ACCOUNT |  | 2021-09-20
BUGIS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | PAI NEE WONG | YU XUEN NG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Sharon assist in AWP for revenue and TOC based on the 50 contract, Yu Xuen will provide guidance | 2021-09-01
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-25 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-20
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | EMILY GOH, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-10-04 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-09-27
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-21
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-19 | WIP | Quarter 1 and quarter 2 (interim AUP) | 2021-10-16
GAIN CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN | ML quarter and Application view no yet received | 2021-09-20
GAIN CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
GM CREDITZ PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
GM CREDITZ PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, SHARON WONG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Emily to assist on AWP for revenue and TOC based on the 50 contract, Jacinth to guide. | 2021-09-01
GT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
GT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Jacinth to provide guidance | 2021-09-01
HAPPY CASH PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
HAPPY CASH PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, SHARON WONG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Jacinth to provide guidance | 2021-09-01
JEFFLEE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | YU XUEN NG | EMILY GOH, YONG LAM NG | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | PLANNING COMPLETED - WITH ACCOUNT |  | 2021-09-20
JEFFLEE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Emily to assist on AWP for revenue and TOC, Jacinth to provide guidance | 2021-09-01
KARTHIK MONEY LENDING PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
KARTHIK MONEY LENDING PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-12-31 | 40 | 2021-12-31 | ACCOUNT NOT IN | Interim - To assist on AWP for revenue and TOC, Jacinth to provide guidance | 2021-09-01
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | EMILY GOH, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2021-09-29 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-22
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-31 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-28
MM CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | INTERIM COMPLETED |  | 2021-09-20
MM CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Emily to assist on AWP for Revenue and TOC, Jacinth to provide guidance | 2021-09-01
NEW ERA CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | MUI LING TAN | EMILY GOH, MUI LING TAN | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program - in progress | 2021-09-22
PERIAKARUPPAN CHETTIAR PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-10-04
PERIAKARUPPAN CHETTIAR PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH, YONG LAM NG | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
PIT-STOP CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
PIT-STOP CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, SHARON WONG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
PR VR CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | YONG LAM NG, EMILY GOH | 2021-12-31 |  |  | 20 | 2021-10-15 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-09-20
PR VR CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-10-04
PROSPER CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | INTERIM COMPLETED |  | 2021-09-20
PROSPER CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, SHARON WONG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
QV CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH | 2021-12-31 | 2020-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
QV CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | HAO YAN, EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-01 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) - Done by Emily on 27 Sep To be review by Victoria | 2021-09-24
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-10-01 | ACCOUNT NOT IN | Roll forward AWP and audit programme - completed on 30/9/2021 | 2021-09-24
SGP CREDIT SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-08 | 16 | 2021-09-10 | ACCOUNT NOT IN | Follow up ML return and application view from client @28 Sep Roll forward AWP and audit programme - in progress | 2021-09-20
SGP CREDIT SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN | ML return and Application no yet received, follow up @ 29 Sep | 2021-09-20
SIGHAPPI ACHI MONEYLENDER (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 16 | 2021-10-31 | ACCOUNT NOT IN | Only one contract | 2021-09-01
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-27
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | EMILY GOH, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-12
SWIFT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
THE MONEYLENDERS PTE LTD | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-08 | 16 | 2021-10-08 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress No loan during the year | 2021-09-20
UNILINK CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN | Request softcopy | 2021-09-20
UNILINK CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
UNIQCASH PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward AWP & Audit Program - completed 1/10/2021 | 2021-09-21