## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-20 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done @ 10/1/2021 | 2021-09-13
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 40 | 2021-10-07 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-04
2J HOLDINGS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | KWEH CHUN SHENG, HAO YAN | 2021-03-31 | 2021-08-16 | 2021-09-30 | 80 | 2021-09-15 | CLEARING REVIEW POINTS | Received Review Dated 20/9/2021, Clearing Review Points. Sent Confirmation Dated 21/9/2020 | 2021-08-17
A&O FARMERS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | HAO YAN, LOK YEE RENNIE THEW | 2021-03-31 | 2021-08-16 | 2021-09-30 | 40 | 2021-08-27 | REVIEWING - MANAGER | Queries raised and sent by 19-8-21; Queries replied by Mr Thomas @ 20-8-21 (partial); **Pending the 5Q(queries) replied from Siew Ee; Replied by Siew Ee @23-8-21; Will proceed before 1-9-2021; Pending documents from clients, wait for reply (3/9/2021), Replied by SiewEe on 8/9/2021 Send to Felicia review @ 10/9/21, Review Comments by Felicia @ 16/9/21. Pending queries reply from Siew Ee @20/9/21, send to Felicia for 2nd review @ 20/9/21. Queries replied (half) on 24/09/21. Queries sent on | 2021-08-17
A1 CREDIT SG PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | MUI LING TAN | HAO YAN, MUI LING TAN | 2021-12-31 |  |  | 80 | 2021-09-17 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done @10/1/2021 | 2021-09-13
ANDAL ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | YU XUEN NG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
APPLE PROMESSA MEDIA STUDIO SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | HAO YAN | HAO YAN | 2021-03-31 | 2021-09-13 | 2021-09-30 | 30 | 2021-09-30 | CLEARING REVIEW POINTS | Queries sent on 27.09.21; For Mr. Ray review @ 28.09.21; Pass back @ 30.09.21 | 2021-09-17
APPLE PROMESSA MEDIA STUDIO SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | HAO YAN | HAO YAN | 2021-03-31 | 2021-09-13 | 2021-09-30 | 8 | 2021-09-30 | YET TO START | Request soft copy account @20/9/21, start @ 21/9/21 | 2021-09-20
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-21 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-14
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | HAO YAN, PIK EN TOH | 2021-12-31 |  |  | 40 | 2021-10-19 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-16
BUGIS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | PAI NEE WONG | YU XUEN NG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Sharon assist in AWP for revenue and TOC based on the 50 contract, Yu Xuen will provide guidance | 2021-09-01
CRAWFORT PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-21 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-15
EMVERTEX CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | HAO YAN, MUI LING TAN | 2021-12-31 |  |  | 80 | 2021-09-23 | ACCOUNT NOT IN | Roll forward AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-17
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-24 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-17
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 40 | 2021-10-15 | WIP | Client sent in softcopy Quarter 1 and quarter 2 (interim AUP) | 2021-10-12
GOLDEN CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-24 | ACCOUNT NOT IN | Roll forward AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-20
HHL CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-24 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-20
KAIIRON PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-27 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-21
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | HAO YAN, SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-10-11 | WIP | Sent in softcopy, assigned to Hao Yan Quarter 1 and quarter 2 (interim AUP) | 2021-10-08
LIAN FONG CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | CHIA EN CHEONG | HAO YAN, SHARON WONG | 2021-12-31 |  |  | 80 | 2021-09-27 | ACCOUNT NOT IN | Roll forward for AWP and Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-21
MM CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Emily to assist on AWP for Revenue and TOC, Jacinth to provide guidance | 2021-09-01
OT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-22
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-30 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-23
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG | 2021-12-31 |  |  | 40 | 2021-10-23 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-20
QV CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | HAO YAN, EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2021-10-01 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-24
SIGHAPPI ACHI MONEYLENDER (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 16 | 2021-10-31 | ACCOUNT NOT IN | Only one contract | 2021-09-01
SWIFT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
UNILINK CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | PAI NEE WONG | SOO WUEN ONG | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
WINZ CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-28