## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
A1 CREDIT SG PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | MUI LING TAN | HAO YAN, MUI LING TAN | 2021-12-31 |  |  | 80 | 2021-09-17 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done @10/1/2021 | 2021-09-13
A1 CREDIT SG PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | HWEE XIN LIM | MUI LING TAN | MUI LING TAN | 2021-12-31 |  |  | 40 | 2021-10-15 | WIP | for 2 quarters only | 2021-10-11
ADVANCE CASH CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | HWEE XIN LIM | KOK YEE CHOONG | EMILY GOH, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-20 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program - In progress | 2021-09-14
ADVANCE CASH CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2021-12-31 |  |  | 40 | 2021-10-08 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-04
AMEDEO RESOURCES (ASIA) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2019-12-31 | 2020-07-16 | 2020-08-29 | 40 | 2021-06-30 | PENDING DOCS & PAYMENT | Pending payment and document Pending letter of support from Holding Company Email Follow up: 14/12/2020 Email follow up: 2/5/2021 | 2020-07-16
BAZE MARINE & OFFSHORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | TIONG YAW TAN | TIONG YAW TAN | 2021-03-31 | 2021-06-01 | 2021-09-30 | 50 | 2021-08-31 | SENT OUT FOR ADOPTION |  | 2021-08-23
BONANZA101 PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | HWEE XIN LIM | HWEE XIN LIM | 2020-12-31 | 2021-03-15 | 2021-06-30 | 25 | 2021-04-30 | PENDING PAYMENT | 7/6/21 - Submit for partner review | 2021-04-06
BTB CREDITZ PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | SHARON WONG, CHIA EN CHEONG | 2021-12-31 |  |  | 80 | 2021-09-21 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.)In progress the roll over the audit program | 2021-09-15
BTB CREDITZ PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG | 2021-12-31 |  |  | 40 | 2021-10-08 | WIP | for 2 quarters only | 2021-10-04
CAPITAL C CORPORATION PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | JACINTH LOI KAI CHEE | 2020-12-31 | 2021-07-19 | 2021-06-30 | 100 | 2021-08-31 | KIV | 20/08 - Planning done, AWP roll over. 12/08 - Account sent in, interco not tallied and pending client to amend 14/9 - OSM meeting with client, pending client to provide documents. Pending section on Interco, PPE, EBE, Statutory records, revenue invoices. 28/9 - Followed up with client, pending reply | 2021-08-09
CAPITAL C PEOPLE XPERIENCE PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | MUI LING TAN | 2020-12-31 | 2021-07-19 | 2021-06-30 | 60 | 2021-08-31 | WIP | 12/8 - Account sent in without audit schedule & GL, followed up with client | 2021-08-09
CAPITALL AUTO FINANCIAL SERVICES PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | WEI QI YU | 2020-12-31 | 2021-08-20 | 2021-06-30 | 60 | 2021-09-17 | KIV |  | 2021-08-20
CAPITALL PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | WEI QI YU | 2020-12-31 | 2021-07-19 | 2021-06-30 | 70 | 2021-08-31 | KIV |  | 2021-08-02
CENTRE LINK TRAVEL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | HWEE XIN LIM | HWEE XIN LIM, LAY CHIAN GAN | 2020-12-31 | 2021-03-19 | 2021-06-30 | 60 | 2021-04-16 | PENDING DOCS | 28/6 - Pending signed letter of engagement and AJE | 2021-05-05
CNC DESIGN PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | TIONG YAW TAN | CHIA EN CHEONG, TIONG YAW TAN | 2020-06-30 | 2021-04-26 | 2021-06-30 | 100 | 2021-08-31 | WIP | 1/10 - Pending project P&L from client | 2021-08-02
CRAWFORT PTE. LTD. | ACUMEN ASSURANCE | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-01-25 | 2021-04-30 | 40 | 2021-07-31 | PENDING PAYMENT | Client keep dragging the payment | 2021-01-25
CRAWFORT PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | PIK EN TOH | YING QIN YONG, PIK EN TOH | 2020-12-31 | 2021-02-19 | 2021-03-31 | 80 | 2021-07-31 | PENDING DOCS & PAYMENT | Client keep dragging the payment | 2021-02-19
CRAWFORT PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-21 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-15
CRAWFORT PTE. LTD. | ACUMEN ASSURANCE | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-11
EDG DESIGN - ASIA PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LAWRENCE CHEN TSE CHAU | HWEE XIN LIM | HWEE XIN LIM | HWEE XIN LIM, YIN YING LOW, BIN GUI TAN | 2019-12-31 | 2020-08-11 | 2020-08-31 | 50 | 2021-02-26 | KIV | 30/6 - Client not agree with Disclaimer Opinion. Email sent to client the issue and waiting for their reply or arrange zoom meeting 2 Feb - File submitted for 2nd review 26 Jan - file return from manager 18 Jan - submit file to manager for review 15 Jan - able to finalise the AWP and report, will submit on earlier of next week 17 Dec - Pending supporting doc and info from client 15 Dec - Meeting | 2020-08-21
EDUBASE TRAINING CONSULTANCY PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | YU XUEN NG | YU XUEN NG, JOANNE TEH HUI LING | 2019-12-31 | 2020-11-24 | 2020-12-31 | 60 | 2021-03-31 | WIP |  | 2020-11-25
EMVERTEX CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | HAO YAN, MUI LING TAN | 2021-12-31 |  |  | 80 | 2021-09-23 | ACCOUNT NOT IN | Roll forward AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-17
EMVERTEX CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | MUI LING TAN | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-11
ENE HI-TECH ENGINEERING PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | JACINTH LOI KAI CHEE | JACINTH LOI KAI CHEE | 2017-12-31 | 2021-01-20 |  | 70 | 2021-03-31 | KIV |  | 2021-01-20
FAST MONEY PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | SHARON WONG, CHIA EN CHEONG | 2021-12-31 |  |  | 80 | 2021-10-05 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-29
FAST MONEY PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-11
FAST RECOVERY (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | KWEH CHUN SHENG, CHIA EN CHEONG | 2021-12-31 |  |  | 80 | 2021-10-05 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program | 2021-09-29
FUTURIX PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | PIK EN TOH | YONG LAM NG, PIK EN TOH | 2021-03-31 | 2021-07-02 | 2021-09-30 | 90 | 2021-09-10 | REVIEWING - MANAGER |  | 2021-08-23
GOLDEN CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-24 | ACCOUNT NOT IN | Roll forward AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-20
GOLDEN CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2021-12-31 |  |  | 40 | 2021-10-08 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-04
GT CREDIT PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | JACINTH LOI KAI CHEE | 2020-12-31 | 2021-02-08 | 2021-04-30 | 40 | 2021-03-12 | PENDING PAYMENT | 16/7/2021 - report signed, pending payment 7/7/2021 - Sent out for adoption 5/7/2021 - Submit for review 3/5/2021 - WIP 27/4/2021 - Fieldwork AUP STT SAVE UNDER DROPBOX AAAPL>AALLP>AUDIT OF MONEYLENDER>2020>AUP FYE 2020 | 2021-02-09
HHL CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-24 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-20
HHL CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG | 2021-12-31 |  |  | 40 | 2021-10-15 | PLANNING WITH ACCOUNT | for 2 quarters only | 2021-10-11
HOTEL AIRLINES SERVICES PTE LTD | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | YU XUEN NG | YU XUEN NG | 2019-12-31 |  | 2020-08-29 | 30 | 2021-03-31 | PENDING PAYMENT | Followed up payment on 22/2. | 2020-07-06
JNB CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | HWEE XIN LIM | PUI SHI LEE | PUI SHI LEE, YONG LAM NG, LI FANG ANGELA CHAI | 2020-12-31 |  | 2021-07-31 | 80 | 2021-07-09 | CLEARING REVIEW POINTS | Draft audited FS | 2021-07-05
KAIIRON PTE. LTD. | ACUMEN ASSURANCE | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2020-12-31 | 2021-01-25 | 2021-04-30 | 40 | 2021-06-30 | PENDING PAYMENT | Pending payment | 2021-01-25
KAIIRON PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | JOANNE TEH HUI LING, KOK YEE CHOONG | 2020-12-31 | 2021-03-25 | 2021-04-30 | 80 | 2021-06-30 | PENDING PAYMENT | Pending payment | 2021-03-25
KAIIRON PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-09-27 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-21
KAIIRON PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | KOK YEE CHOONG | YONG LAM NG, KOK YEE CHOONG | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-11
KRDF03 PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | HWEE XIN LIM | HWEE XIN LIM | 2020-12-31 | 2021-03-15 | 2021-06-30 | 50 | 2021-05-31 | PENDING PAYMENT | Audit S$2,500 Review of subsi S$7,000 Conso S$2,500 18/7 - Client has applied for extension and pending subsidiary information | 2021-04-06
LIAN FONG CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | CHIA EN CHEONG | HAO YAN, SHARON WONG | 2021-12-31 |  |  | 80 | 2021-09-27 | ACCOUNT NOT IN | Roll forward for AWP and Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-21
LIAN FONG CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | HWEE XIN LIM | CHIA EN CHEONG | SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-08 | INTERIM COMPLETED | for 2 quarters only Completed AWP AUP on 24/9/2021 | 2021-10-04
LINKOIL PETROLEUM AND CHEMICALS PTE LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | PUI SHI LEE | PUI SHI LEE | 2021-03-31 | 2021-06-09 | 2021-09-30 | 120 | 2021-07-07 | PENDING PAYMENT | Pending Payment | 2021-06-14
LUMINOUS DENTAL GROUP HOLDINGS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | KOK YEE CHOONG | JACINTH LOI KAI CHEE, KOK YEE CHOONG | 2017-12-31 | 2021-01-20 |  | 120 | 2021-03-31 | KIV | Latest set of audit queires sent on 30 July 2021 | 2021-01-20
MAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | MUI LING TAN, SHARON WONG | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.)In progress the roll over the audit program | 2021-09-22
MAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | MUI LING TAN | 2018-10-31 |  |  | 40 | 2021-10-08 | WIP | for 2 quarters only | 2021-10-04
MENG SENG (S) PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | HWEE XIN LIM | YING QIN YONG, KOK CHIN CHAN | 2019-12-31 | 2020-07-20 | 2020-08-31 | 50 | 2021-04-30 | KIV | 12.01.2021-Email to George for update. 11.01.2021-Email to George to update audit queries as he havent aswer the audit queries. 30.12.2020-Email and called George for audit queries, he will reply the queries by next week. 11.12.2020 - Received only sales invoices, queries have not been answer yet. 26.11.2020 - Called to Mr Chong to ask for queries and second time send out audit queries. 18.11.2020 - Audit queries sent out to George Chong 13.11.2020 - Transferred to Renyx. 14.10.2020 - Fol | 2020-08-03
NEW ERA CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | MUI LING TAN | EMILY GOH, MUI LING TAN | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program - in progress | 2021-09-22
NEW ERA CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | HWEE XIN LIM | MUI LING TAN | MUI LING TAN, YONG LAM NG | 2021-12-31 |  |  | 40 | 2021-10-22 | WIP | for 2 quarters only | 2021-09-24
OT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-22
OT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG | 2021-12-31 |  |  | 40 | 2021-10-08 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-04
POLY COLOR AND COMPOUNDS (SINGAPORE) PRIVATE LIMITED | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | WEI QI YU | WEI QI YU | 2021-03-31 | 2021-06-28 | 2021-09-30 | 16 | 2021-08-27 | SENT OUT FOR ADOPTION |  | 2021-08-23
S G CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | MUI LING TAN | 2020-12-31 | 2021-01-25 | 2021-04-30 | 40 | 2021-03-15 | PENDING PAYMENT | AUP STT SAVE UNDER DROPBOX AAAPL>AALLP>AUDIT OF MONEYLENDER>AUP FYE 2020 | 2021-01-25
S G CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | JACINTH LOI KAI CHEE | JOANNE TEH HUI LING, MUI LING TAN | 2020-12-31 | 2021-02-19 | 2021-04-30 | 80 | 2021-03-19 | PENDING PAYMENT | mgmt account, report, awp kept under aaa folder>0 singapore job> ML audit Mapping done. But audit yet to start | 2021-02-19
S G CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | SHARON WONG, CHIA EN CHEONG | 2019-03-31 |  |  | 80 | 2021-09-30 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-24
S G CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | CHIA EN CHEONG | YONG LAM NG, CHIA EN CHEONG | 2021-12-31 |  |  | 40 | 2021-10-08 | WIP | for 2 quarters only | 2021-09-24
SATEJ INTERNATIONAL RESOURCES PRIVATE LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | CHIN YING CHEW, SHU WEN CHAN, KOK YEE CHOONG | 2019-03-31 | 2020-09-18 | 2020-11-30 | 65 | 2021-09-30 | SENT OUT FOR ADOPTION | Pending signing pages and related confirmation. Last follow up: 21 Sept 2021 | 2020-10-28
SHANMUGAN MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | CHIA EN CHEONG | SHARON WONG | 2021-12-31 |  |  | 80 | 2021-09-30 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-24
SHANMUGAN MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | HWEE XIN LIM | CHIA EN CHEONG | SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | for 2 quarters only 1.) Follow up with client on 23/9/2021 2.) Reply by client on 24/9/2021 (Client had engaged some issue so will take time, the director will reply once issue is settle) | 2021-10-11
SOHETO (SINGAPORE) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | YU XUEN NG | YING QIN YONG, LAY CHIAN GAN, YU XUEN NG, JOANNE TEH HUI LING | 2020-12-31 | 2021-03-18 | 2021-06-30 | 90 | 2021-05-26 | PENDING DOCS | Pending documents from client | 2021-05-10
STOKED ASSOCIATES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | KOK YEE CHOONG | MUI LING TAN, KOK YEE CHOONG | 2019-12-31 | 2021-04-06 | 2021-06-30 | 70 | 2021-06-11 | KIV | Account will be revised. Targeted receive date: 24 Sept 2021 | 2021-04-28
SYNERGY LI CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG, CHIN YING CHEW, SHU WEN CHAN | 2019-03-31 | 2020-09-18 | 2020-11-30 | 45 | 2021-09-30 | SENT OUT FOR ADOPTION | Pending signing pages and related confirmation. Last follow up: 21 Sept 2021 | 2020-10-28
SYNERGY LI CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG, CHIN YING CHEW | 2020-03-31 | 2020-09-18 | 2020-12-31 | 45 | 2021-09-30 | SENT OUT FOR ADOPTION | Pending signing pages and related confirmation. Last follow up: 21 Sept 2021 | 2020-12-11
SYNERGY LI INTERNATIONAL RESOURCES LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG, CHIN YING CHEW, SHU WEN CHAN | 2019-03-31 | 2020-09-18 | 2020-11-30 | 45 | 2021-09-30 | SENT OUT FOR ADOPTION | Pending signing pages and related confirmation. Last follow up: 21 Sept 2021 | 2020-10-28
SYNERGY LI INTERNATIONAL RESOURCES LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG, CHIN YING CHEW | 2020-03-31 | 2020-09-18 | 2020-12-31 | 45 | 2021-09-30 | SENT OUT FOR ADOPTION | Pending signing pages and related confirmation. Last follow up: 21 Sept 2021 | 2020-12-11
TONG SIAN TNG TEMPLE | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2020-12-31 | 2021-06-11 | 2021-06-30 | 24 | 2021-07-09 | SIGNED | Meet with partner: 3 September 2021 | 2021-06-29
TUR MOHAR MONEY LENDING PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG, SHARON WONG | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-27
TUR MOHAR MONEY LENDING PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG, YONG LAM NG | 2021-12-31 |  |  | 40 | 2021-10-15 | WIP | for 2 quarters only | 2021-09-24
UNIQCASH PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-28 | ACCOUNT NOT IN | Roll forward AWP & Audit Program - completed 1/10/2021 | 2021-09-21
UNIQCASH PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | MUI LING TAN | 2021-12-31 |  |  | 40 | 2021-10-22 | ACCOUNT NOT IN | For 2 quarters first | 2021-10-18
UNLIMITED FINANCE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | SHARON WONG | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program 1.) Completed the roll forward for AWP 2.)In progress the roll over the audit program | 2021-09-28
UNLIMITED FINANCE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | HWEE XIN LIM | MUI LING TAN | MUI LING TAN | 2021-12-31 |  |  | 40 | 2021-10-08 | WIP | for 2 quarters only | 2021-10-04
UTAC HEADQUARTERS PTE. LTD. | ACUMEN ASSOCIATES LLP | OTHERS | WOELLY WILLIAM | HWEE XIN LIM | TAT WAI DAVID LEE | YING QIN YONG, TAT WAI DAVID LEE |  | 2021-05-17 | 2021-05-31 | 60 | 2021-06-04 | KIV | 3 ENGAGEMENTS (COVER DIFFERENT PERIOD - REFER TO LETTER OF AWARD - DO NOT RELY ON THE PERIOD MENTIONED IN THIS ASSIGNMENT SYSTEM) 1. IMAGE SENSOR MOLDED PACKAGE - 20HRS 2. PACT - 20 HRS 3. RISC PLASMA DICING - 20 HRS | 2021-05-18
WINZ CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | KOK YEE CHOONG | HAO YAN, KOK YEE CHOONG | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward for AWP & Audit Program; Done for AWP, audit program in progress @10/1/2021 | 2021-09-28
WINZ CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | HWEE XIN LIM | KOK YEE CHOONG | KOK YEE CHOONG | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | for 2 quarters only | 2021-10-11
WORLD PROPERTIES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | HWEE XIN LIM | CHIA EN CHEONG | CHIA EN CHEONG | 2021-06-30 | 2021-09-13 | 2021-12-31 | 60 | 2021-09-30 | KIV |  | 2021-09-14
YONG LI INTERNATIONAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | A GARANZIA | HWEE XIN LIM | HWEE XIN LIM | HWEE XIN LIM | 2019-12-31 |  |  | 90 | 2021-03-12 | PENDING PAYMENT | 1/3/21 - per George, client will settle by this week | 2020-04-01