## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | SHARON WONG, PIK EN TOH | 2021-12-31 |  |  | 80 | 2021-09-20 | PLANNING WITH ACCOUNT | Completed roll forward AWP and generate from system (audit program) 1.) Completed the roll forward for AWP 2.)Completed the roll over for audit program | 2021-09-13
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-23 | KIV | Quarter 1 and quarter 2 (interim AUP) Pending client reply on fieldwork date | 2021-10-20
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-20 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done @ 10/1/2021 | 2021-09-13
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 40 | 2021-10-07 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-04
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-18 | ACCOUNT NOT IN | Roll forward AWP and audit programme - completed on 6/10/2021 | 2021-09-13
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-11 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-10-08
2J HOLDINGS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | KWEH CHUN SHENG, HAO YAN | 2021-03-31 | 2021-08-16 | 2021-09-30 | 80 | 2021-09-15 | REVIEWING - PARTNER | Submitted for partner review (Company level) @ 8 Oct 21 | 2021-08-17
A&O FARMERS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | HAO YAN, LOK YEE RENNIE THEW | 2021-03-31 | 2021-08-16 | 2021-09-30 | 40 | 2021-08-27 | SENT OUT FOR ADOPTION | Sent out adoption on 12 Oct Queries raised and sent by 19-8-21; Queries replied by Mr Thomas @ 20-8-21 (partial); Replied by Siew Ee @23-8-21; Pending documents from clients(3/9/2021), Replied by SiewEe on 8/9/2021 Send to Felicia review @ 10/9/21, Review Comments by Felicia @ 16/9/21. Pending queries reply from Siew Ee @20/9/21, send to Felicia for 2nd review @ 20/9/21. Queries replied (half) on 24/09/21. Submit for partner review @ 7/10/21; 2nd review @ 12/10/21 | 2021-08-17
AK CREDIT CORPORATION PTE. LTD. |  | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | SHARON WONG, YONG LAI WONG | 2019-03-31 |  |  | 80 | 2021-09-21 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-14
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-11-04 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-11-01
ASIA PACIFIC BIOINFORMATICS NETWORK LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | MUI LING TAN | MUI LING TAN | 2020-12-31 | 2021-05-19 | 2021-06-30 | 40 | 2021-06-16 | PENDING PAYMENT |  | 2021-06-07
ASIAN GOLF INDUSTRY FEDERATION | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PUI SHI LEE | 2021-06-30 | 2021-09-29 | 2021-12-31 | 80 | 2021-11-01 | ACCOUNT NOT IN | Job assigned to Pui Shi on 1 Oct 2021 Account received on 29 Sep 2021 | 2021-10-06
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 80 | 2021-09-21 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program Pending trial balance and GL for interim audit | 2021-09-14
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-19 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) Pending client reply to provide loan samples | 2021-10-16
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-21 | PLANNING WITH ACCOUNT | Roll forward AWP and audit programme; Done for AWP and audit programme Pending client reply on fieldwork date | 2021-09-14
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | HAO YAN, PIK EN TOH | 2021-12-31 |  |  | 40 | 2021-10-19 | PENDING DOCS | Quarter 1 and quarter 2 (interim AUP) Pending client reply on fieldwork date | 2021-10-16
BL PROJECTS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG | 2020-12-31 | 2021-07-02 | 2021-06-30 | 90 | 2021-08-31 | WIP | Yet to start. Planning meeting with partner on 18.08. TBC with Ray Kong for the AR filing extension. WIP. OSM sent. Currently, client serving QO from MOH and inform to be released on next week. OSM replied on 05.10. WIP Updated on 07.10 | 2021-08-02
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-22 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-15
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-04 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) - samples sent in, Emily is performing vouching | 2021-09-28
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-25 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-20
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | EMILY GOH, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-10-04 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-09-27
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2021-09-22 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-15
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-27 | WIP | Quarter 1 and quarter 2 (interim AUP). Received softcopies for selected contracts. Overall contract checked. only few need to get additional supporting from client. Updated 0n 14.10 | 2021-10-24
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | YU XUEN NG | 2019-12-31 | 2020-10-12 | 2020-11-30 | 60 | 2021-03-15 | PENDING DOCS | Pending signing doc. Follow up on 23/8 | 2020-10-29
CONVERSANT GLOBAL PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-08 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | Finalising working paper and draft report | 2021-03-23
CONVERSANT INVESTMENT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | XUN HUI SOH | XUN HUI SOH, SU HUI TAN | 2019-12-31 | 2020-05-22 | 2020-06-30 | 20 | 2021-03-12 | PENDING DOCS | Sent out adoption on 14 Oct Sent for partner review in softcopy on 26 June | 2020-06-05
CONVERSANT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-11 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | Amendment to do | 2021-03-23
CONVERSANT SOLUTIONS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | MUI LING TAN, YU XUEN NG, PIK EN TOH | 2020-12-31 | 2021-03-03 | 2021-06-30 | 100 | 2021-07-31 | SENT OUT FOR ADOPTION | Amendment done on 31 Aug | 2021-03-24
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-09-28 | PLANNING WITHOUT ACCOUNT | Roll forward AWP and audit programme - in progress | 2021-09-21
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-19 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-10-16
CREDIT XTRA PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 80 | 2021-09-24 | PLANNING WITHOUT ACCOUNT | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-17
CREDIT XTRA PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-15 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) 1.) Completed AWP AUP | 2021-10-12
EVERMARK INTERNATIONAL (PTE.) LIMITED | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2021-05-31 | 2021-08-31 | 2021-11-30 | 50 | 2021-09-17 | KIV | Pending reply for audit queries and supporting documents from client | 2021-09-06
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-24 | PLANNING WITHOUT ACCOUNT | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-17
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 40 | 2021-10-15 | REVIEWING - MANAGER | Client sent in softcopy Quarter 1 and quarter 2 (interim AUP); AUP done @ 4/10/21 | 2021-10-12
GLOBAL LNC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SHARON WONG, KWEH CHUN SHENG | 2021-03-31 | 2021-08-20 | 2021-09-30 | 35 | 2021-08-27 | SENT OUT FOR ADOPTION | Sent for adoption on 12 Oct Queries sent by 3/9/2021 10:32am and pending documents from client. Follow up the documents on Wednesday 8/9/2021 10:33am. Received documents on Thursday 9/9/2021 3.10pm | 2021-08-23
GLOBAL OCEANLINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, SOO WUEN ONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 140 | 2021-08-31 | SENT OUT FOR ADOPTION | 2nd review @ Manager @ 11 Oct 21 1st review @ Partner @ 12 Oct 21 Sent for adoption @ KIV supporting for online sale @ 13 Oct 21 | 2021-08-02
HDR PAYMENT PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-06-11 | 2021-08-31 | 100 | 2021-09-30 | PENDING DOCS | Extension filed Audit for 2019 (opening) and 2020 | 2021-08-01
HDR SG PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2020-12-31 | 2021-06-11 | 2021-08-31 | 8 | 2021-09-30 | PENDING DOCS | 2 MTHS EXTENSION FILED FIRST SET OF FS | 2021-08-01
HHL CREDIT PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH |  |  |  | 24 | 2021-08-31 | FINALIZING | To print working paper and submit to partner | 2020-08-20
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | SHARON WONG, WEI QI YU | 2021-08-31 |  |  | 80 | 2021-09-28 | PLANNING WITHOUT ACCOUNT | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.)In progress the roll over the audit program | 2021-09-21
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | HAO YAN, SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-10-11 | REVIEWING - MANAGER | Sent in softcopy, assigned to Hao Yan Quarter 1 and quarter 2 (interim AUP); AUP done @ 4/10/21 | 2021-10-08
LMB AEROSPACE ASIA PACIFIC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2021-06-30 | 2021-07-06 | 2021-12-31 | 60 | 2021-08-31 | REVIEWING - MANAGER |  | 2021-07-26
LUMIPLAN ASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YING QIN YONG | CHIA EN CHEONG, YING QIN YONG | 2021-03-31 | 2021-06-17 | 2021-09-30 | 60 | 2021-07-30 | SENT OUT FOR ADOPTION |  | 2021-07-23
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | EMILY GOH, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2021-09-29 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-22
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-31 | PLANNING WITHOUT ACCOUNT | Quarter 1 and quarter 2 (interim AUP). Client is preparing selected samples and will inform once is ready. Updated on 07.10. | 2021-10-28
NOVEL COMMUNICATION PTE. LTD. | SYA PAC | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, KOK YEE CHOONG | 2020-12-31 | 2021-05-07 | 2021-06-30 | 110 | 2021-06-23 | SENT OUT FOR ADOPTION | Fieldwork start on 12.08.21, WIP on 27.08.21, pending query from client, go through the response from client for previous query | 2021-06-10
NUTRIXPERTS PTE. LTD. (FORMERLY KNOWN AS LISA RD SINGAPORE PTE. LTD.) | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-09-03 | 2020-09-30 | 40 | 2021-04-30 | FINALIZING | Updated outstanding to client @ 22 Sep 21 Follow up @29 Sep 21 Client replied @ 30 Sep 21 | 2020-09-07
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 80 | 2021-09-29 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-22
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2020-12-31 |  |  | 40 | 2021-10-31 | WIP | Quarter 1 and quarter 2 (interim AUP) | 2021-10-28
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, HAO YAN | 2021-12-31 |  |  | 80 | 2021-09-30 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-23
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG | 2021-12-31 |  |  | 40 | 2021-10-23 | PLANNING COMPLETED - WITH ACCOUNT | Quarter 1 and quarter 2 (interim AUP). Sample selection sent, awaiting client to prepare. Updated on 14.10. | 2021-10-20
PROCESS TECHNOLOGY CONSULTANTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | WEI QI YU, XUN HUI SOH | 2021-03-31 | 2021-06-09 | 2021-09-30 | 60 | 2021-07-30 | PENDING DOCS & PAYMENT | 1. Account received on 9 June 2021 | 2021-06-25
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-10-01 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) - Done by Emily on 27 Sep To be review by Victoria | 2021-09-24
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-10-01 | PLANNING WITH ACCOUNT | Roll forward AWP and audit programme - completed on 30/9/2021 Planning with trial balance and GL | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2021-10-01 | ACCOUNT NOT IN | Roll forward AWP and audit programme; Done for AWP, audit program in progress @10/1/2021 | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-10-01 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-09-24
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward AWP and audit programme - in progress | 2021-09-27
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | EMILY GOH, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-10-15 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-12
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 80 | 2021-10-04 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-27
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-10-04 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) 1.) No interim AUP for SME care, no loan issue as at June 2021 | 2021-09-27
SUPREME LINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, JIA XIAN FOONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 70 | 2021-08-31 | REVIEWING - MANAGER |  | 2021-08-02
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-11-04 | 2020-11-30 | 70 | 2021-03-31 | PENDING DOCS | All copies signed, pending cor sec document to be received. | 2020-11-23
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | YU XUEN NG, SOO WUEN ONG | 2020-12-31 | 2021-03-09 | 2021-06-30 | 80 | 2021-07-31 | SENT OUT FOR ADOPTION | To sent for adoption with other companies | 2021-03-23
THE MASONIC HALL BOARD LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2020-12-31 | 2021-04-26 | 2021-07-31 | 50 | 2021-07-29 | REVIEWING - MANAGER |  | 2021-07-22
UNIQCASH PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG |  | 2021-02-22 | 2021-04-30 | 20 | 2021-05-31 | FINALIZING | PMFT report obtained. will schedule one day for wrapping up. | 2021-02-22