## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | SHARON WONG, PIK EN TOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | - Samples (TOC and revenue) sent to client - Pending reply for fieldwork date | 2021-09-13
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | KIV | Quarter 1 and quarter 2 (interim AUP) Pending client reply on fieldwork date | 2021-10-20
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | YET TO START | Roll forward AWP and audit programme; Done @ 10/1/2021 | 2021-09-13
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Quarter 1 and quarter 2 (interim AUP) | 2021-10-04
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | YET TO START | Roll forward AWP and audit programme - completed on 6/10/2021 | 2021-09-13
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-10-08
2J HOLDINGS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | KWEH CHUN SHENG, HAO YAN | 2021-03-31 | 2021-08-16 | 2021-09-30 | 80 | 2021-10-29 | SIGNED | Submitted for partner review (Company level) @ 8 Oct 21 | 2021-08-17
A&O FARMERS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | HAO YAN, LOK YEE RENNIE THEW | 2021-03-31 | 2021-08-16 | 2021-09-30 | 40 | 2021-10-29 | SIGNED | Sent out adoption on 12 Oct Queries raised and sent by 19-8-21; Queries replied by Mr Thomas @ 20-8-21 (partial); Replied by Siew Ee @23-8-21; Pending documents from clients(3/9/2021), Replied by SiewEe on 8/9/2021 Send to Felicia review @ 10/9/21, Review Comments by Felicia @ 16/9/21. Pending queries reply from Siew Ee @20/9/21, send to Felicia for 2nd review @ 20/9/21. Queries replied (half) on 24/09/21. Submit for partner review @ 7/10/21; 2nd review @ 12/10/21 | 2021-08-17
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | JIA XIAN FOONG, SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-14
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | PLANNING COMPLETED - WITHOUT ACCOUNT | Quarter 1 and quarter 2 (interim AUP) Client promise to send in loan contracts by next week. Updated on 28.10 | 2021-11-01
ASIAN GOLF INDUSTRY FEDERATION | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PUI SHI LEE | 2021-06-30 | 2021-09-29 | 2021-12-31 | 80 | 2021-12-31 | KIV | Job assigned to Pui Shi on 1 Oct 2021 Account received on 29 Sep 2021 General Ledger received on 17 Oct 2021. Opening balances of a few account not tally to AFS, ask for reconcile on 22 oct 2021. | 2021-10-06
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | KIV | - Pending documents from client | 2021-09-14
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) Pending client reply to provide loan samples | 2021-10-16
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | PENDING DOCS | - Samples (TOC and revenue) sent to client - Fieldwork on 11 and 12 November 2021 to vouch on expenses and other income, TOC and revenue | 2021-09-14
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | HAO YAN, PIK EN TOH | 2021-12-31 |  |  | 40 | 2021-12-31 | PENDING DOCS | - Samples sent to client to prepare for Q1 - Q3 - Fieldwork on 11 and 12 November 2021 to vouch | 2021-10-16
BL PROJECTS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG | 2020-12-31 | 2021-07-02 | 2021-06-30 | 90 | 2021-11-30 | REVIEWING - MANAGER | Yet to start. Planning meeting with partner on 18.08. TBC with Ray Kong for the AR filing extension. WIP. OSM sent. Currently, client serving QO from MOH and inform to be released on next week. OSM replied on 05.10. WIP Submitted to manager review however client wanted to change the impairment loss. Client passed CLA, amending AWP and will submit to manager review. Pending client confirmation to proceed with final amendment. Reminded on 01.11. Updated on 02.11 | 2021-08-02
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | JUN LOKE, PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | - Samples (TOC and revenue) sent in, to vouch - Fieldwork on 3 November 2021 to vouch on expenses and other income | 2021-09-15
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Quarter 1 and quarter 2 (interim AUP) - samples sent in, Emily is performing vouching | 2021-09-28
BRILLIANCE ALPHA ASSET MANAGEMENT PTE LTD | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2021-09-30 | 2021-10-22 | 2022-01-31 | 80 | 2021-12-15 | YET TO START |  | 2021-10-26
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | JUN LOKE, PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | Roll forward AWP and audit programme - completed on 29/10.2021 | 2021-09-20
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | EMILY GOH, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-09-27
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITH ACCOUNT | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program Planning interim audit. Updated on 28.10 | 2021-09-15
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP). Received softcopies for selected contracts. Overall contract checked. only few need to get additional supporting from client. Updated 0n 14.10 | 2021-10-24
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | YU XUEN NG | 2019-12-31 | 2020-10-12 | 2020-11-30 | 60 | 2021-11-30 | PENDING DOCS | Pending signing doc. Follow up on 23/8 | 2020-10-29
CONVERSANT GLOBAL PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-08 | 2021-06-30 | 120 | 2021-07-31 | SIGNED | Clearing review points with Jessica Report signed and sent to client | 2021-03-23
CONVERSANT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SOO WUEN ONG | 2020-12-31 | 2021-03-11 | 2021-06-30 | 120 | 2021-07-31 | SENT OUT FOR ADOPTION | Sent for adoption | 2021-03-23
CONVERSANT SOLUTIONS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | MUI LING TAN, YU XUEN NG, PIK EN TOH | 2020-12-31 | 2021-03-03 | 2021-06-30 | 100 | 2021-07-31 | CLEARING REVIEW POINTS | Clearing review points with Jessica | 2021-03-24
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | PIK EN TOH, JUN LOKE, WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | To accompany Vicky go fieldwork only | 2021-09-21
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | PIK EN TOH, WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Quarter 1 and quarter 2 (interim AUP) | 2021-10-16
CREDIT XTRA PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITHOUT ACCOUNT | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-17
CREDIT XTRA PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) 1.) Completed AWP AUP | 2021-10-12
EVERMARK INTERNATIONAL (PTE.) LIMITED | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH | 2021-05-31 | 2021-08-31 | 2021-11-30 | 50 | 2021-11-30 | REVIEWING - MANAGER |  | 2021-09-06
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | Roll forward AWP and audit programme; Done for AWP and audit program | 2021-09-17
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Client sent in softcopy Quarter 1 and quarter 2 (interim AUP); AUP done @ 4/10/21 | 2021-10-12
GLOBAL LNC PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SHARON WONG, KWEH CHUN SHENG | 2021-03-31 | 2021-08-20 | 2021-09-30 | 35 | 2021-10-29 | SIGNED | Sent for adoption on 12 Oct Queries sent by 3/9/2021 10:32am and pending documents from client. Follow up the documents on Wednesday 8/9/2021 10:33am. Received documents on Thursday 9/9/2021 3.10pm | 2021-08-23
GLOBAL OCEANLINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, SOO WUEN ONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 140 | 2021-10-29 | SIGNED | 2nd review @ Manager @ 11 Oct 21 1st review @ Partner @ 12 Oct 21 Sent for adoption @ KIV supporting for online sale @ 13 Oct 21 | 2021-08-02
HHL CREDIT PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH |  |  |  | 24 | 2021-08-31 | FINALIZING | To print working paper and submit to partner | 2020-08-20
JOO LEE ENGINEERING PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YONG LAI WONG | WEI QI YU, YONG LAI WONG | 2020-12-31 | 2021-10-28 | 2021-12-31 | 80 | 2021-12-31 | PLANNING WITHOUT ACCOUNT | Account received on 28 October 2021. PBC list sent on 02.11. Updated on 02.11 | 2021-11-01
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | HAO YAN, SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 80 | 2022-03-31 | REVIEWING - TEAM LEAD | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.)In progress the roll over the audit program | 2021-09-21
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | JUN LOKE, HAO YAN, SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - TEAM LEAD | Sent in softcopy, assigned to Hao Yan Quarter 1 and quarter 2 (interim AUP); AUP done @ 4/10/21; AUP Q3 done 21/10/21 | 2021-10-08
LUMIPLAN ASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YING QIN YONG | CHIA EN CHEONG, YING QIN YONG | 2021-03-31 | 2021-06-17 | 2021-09-30 | 60 | 2021-11-30 | SENT OUT FOR ADOPTION |  | 2021-07-23
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | JUN LOKE, HAO YAN, EMILY GOH, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITH ACCOUNT | Planning interim audit with client preliminary account. Updated on 21.10 Rollover & audit program - completed on 31/10/2021 | 2021-09-22
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Quarter 1 and quarter 2 (interim AUP). Client is preparing selected samples and will inform once is ready Updated on 07.10.; AUP Q1Q2 done | 2021-10-11
NUTRIXPERTS PTE. LTD. (FORMERLY KNOWN AS LISA RD SINGAPORE PTE. LTD.) | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | SOO WUEN ONG | 2019-12-31 | 2020-09-03 | 2020-09-30 | 40 | 2021-11-30 | FINALIZING | Client replied @ 13 Oct 21 Send remaining OSM to client @ 21 Oct Follow up @ 2 Nov | 2020-09-07
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-22
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP); AUP Q1Q2 done | 2021-10-11
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITH ACCOUNT | Roll forward AWP and audit programme; Done for AWP and audit program | 2021-09-23
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | PLANNING COMPLETED - WITH ACCOUNT | Quarter 1 and quarter 2 (interim AUP). Sample selection sent, awaiting client to prepare. Updated on 28.10. | 2021-10-20
PROCESS TECHNOLOGY CONSULTANTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | WEI QI YU, XUN HUI SOH | 2021-03-31 | 2021-06-09 | 2021-09-30 | 60 | 2021-10-29 | PENDING DOCS & PAYMENT | 1. Account received on 9 June 2021 | 2021-06-25
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2022-03-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) - Done by Emily on 27 Sep To be review by Victoria | 2021-09-24
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITH ACCOUNT | Roll forward AWP and audit programme - completed on 30/9/2021 Planning with trial balance and GL | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | YET TO START | Roll forward AWP and audit programme; Done for AWP and audit program | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) | 2021-09-24
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme - completed on 28/10/21 | 2021-09-27
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | EMILY GOH, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-12-31 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) | 2021-10-12
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 80 | 2022-03-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-27
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-10-04 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) 1.) No interim AUP for SME care, no loan issue as at June 2021 | 2021-09-27
SUPREME LINK PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | SOO WUEN ONG | YONG LAM NG, JIA XIAN FOONG | 2021-03-31 | 2021-07-30 | 2021-09-30 | 70 | 2021-10-29 | SIGNED |  | 2021-08-02
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | YU XUEN NG, SOO WUEN ONG | 2020-12-31 | 2021-03-09 | 2021-06-30 | 80 | 2021-07-31 | SIGNED | Clearing review points with Jessica Report signed and sent to client | 2021-03-23
THE MASONIC HALL BOARD LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU | 2020-12-31 | 2021-04-26 | 2021-07-31 | 50 | 2021-11-30 | PENDING DOCS & PAYMENT |  | 2021-07-22
UNIQCASH PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG |  | 2021-02-22 | 2021-04-30 | 20 | 2021-05-31 | FINALIZING | PMFT report obtained. will schedule one day for wrapping up. | 2021-02-22