## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
1 2 LEND PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | PAI NEE WONG | TENG HONG LIEW | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | INTERIM COMPLETED | Completed for Q1 to Q3 | 2021-09-20
1 2 LEND PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | TENG HONG LIEW | JUN LOKE, EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
ANDAL ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | PAI NEE WONG | TENG HONG LIEW | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | ACCOUNT NOT IN |  | 2021-09-20
ANDAL ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | PAI NEE WONG | TENG HONG LIEW | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Roll forward for awp and audit programme done; Interim - Emily to assist on AWP for revenue and TOC, Soo Wuen to provide guidance | 2021-09-01
GT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | TENG HONG LIEW | JUN LOKE, EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | ACCOUNT NOT IN | Interim - Emily to assist on AWP for revenue and TOC, Jacinth to provide guidance | 2021-09-01
KARTHIK MONEY LENDING PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | TENG HONG LIEW | EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | INTERIM COMPLETED |  | 2021-09-20
KARTHIK MONEY LENDING PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | TENG HONG LIEW | JUN LOKE, EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-12-31 | 40 | 2021-12-31 | ACCOUNT NOT IN | Interim - To assist on AWP for revenue and TOC, Jacinth to provide guidance Rollover & audit program - completed on 30/10/2021 | 2021-09-01
SIGHAPPI ACHI MONEYLENDER (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | WOELLY WILLIAM | PAI NEE WONG | TENG HONG LIEW | JACINTH LOI KAI CHEE | 2021-12-31 | 2021-09-14 | 2021-10-31 | 2 | 2021-10-31 | INTERIM COMPLETED | One contract only | 2021-09-20
SIGHAPPI ACHI MONEYLENDER (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | TENG HONG LIEW | EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 16 | 2021-10-31 | ACCOUNT NOT IN | Roll forward for awp done and audit programme; Only one contract | 2021-09-01
THREE SIXTY-NINE DEVELOPMENT PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | SOO WUEN ONG | TENG HONG LIEW | 2021-06-30 | 2021-10-04 | 2021-12-31 | 80 | 2021-11-05 | ACCOUNT NOT IN | Take note of the gross loss | 2021-10-12
TORNATECH PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | PAI NEE WONG | JACINTH LOI KAI CHEE | TENG HONG LIEW, YU XUEN NG, JACINTH LOI KAI CHEE | 2021-09-30 | 2021-10-22 | 2022-03-31 | 90 | 2021-11-22 | WIP | 25/10 - Planning meeting done, fieldwork on 1/11/2021 Fieldwork must start on week 4 of Oct First draft 15/11 and final draft 22/11 | 2021-10-25