## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | SHARON WONG, PIK EN TOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | - Samples (TOC and revenue) sent to client - Pending reply for fieldwork date | 2021-09-13
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | PENDING DOCS | - Samples sent to client for Q1 and Q2 - Pending Q3 ML statement | 2021-10-20
101 CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 | 2022-01-11 | 2022-02-28 | 40 | 2022-01-21 | PENDING DOCS | Pending aging report from client, current aging report until 7 Jan 2021 | 2022-01-21
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Roll forward AWP and audit programme; Done @ 10/1/2021 | 2021-09-13
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) | 2021-10-04
1133 MONEYLENDERS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 | 2022-01-18 | 2022-02-28 | 32 | 2022-01-25 | PENDING PAYMENT |  | 2022-01-24
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Roll forward AWP and audit programme - completed on 6/10/2021 | 2021-09-13
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) | 2021-10-08
1ST CAPITAL PTE. LTD. |  | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 | 2022-01-10 | 2022-02-28 | 40 | 2022-01-21 | KIV | Queries sent @ 21/1/22 | 2022-01-21
AGRI OILS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | EMILY GOH | JING HE TAN, EMILY GOH | 2022-03-31 |  |  | 16 | 2021-12-31 | ACCOUNT NOT IN | rollover + audit program completed in 16/11/2021 | 2021-11-01
AILEEN CHONG & CO | ACUMEN ASSOCIATES LLP | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 24 | 2022-02-14 | ACCOUNT NOT IN |  | 2022-01-19
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | JIA XIAN FOONG, SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Interim audit is done only pending arrangement of vouching documents. Updated 09.12 | 2021-09-14
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Contracts received on 02.12. AWP Updated on 09.12 | 2021-11-01
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 |  | 2022-02-28 | 40 | 2022-02-11 | PENDING DOCS | Email follow up on 8/2/22, client working on on the bad debt list. | 2022-01-27
ANCHANTO PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YONG LAI WONG | PUI SHI LEE, YONG LAI WONG, JIA XIAN FOONG | 2021-12-31 | 2022-01-24 | 2022-03-31 | 150 | 2022-03-31 | WIP | 2. Management Account received on 24 January 2022 1. Jia Xian Roll forward of AWP | 2021-11-09
ASIA PACIFIC BIOINFORMATICS NETWORK LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 |  |  | 80 | 2021-11-19 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
ASIAN GOLF INDUSTRY FEDERATION | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PUI SHI LEE | 2021-06-30 | 2021-09-29 | 2021-12-31 | 80 | 2021-12-31 | REVIEWING - MANAGER | Job assigned to Pui Shi on 1 Oct 2021 Account received on 29 Sep 2021 General Ledger received on 17 Oct 2021. Opening balances of a few account not tally to AFS, ask for reconcile on 22 oct 2021. | 2021-10-06
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | KIV | - Pending documents from client | 2021-09-14
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | KIV | Quarter 1 and quarter 2 (interim AUP) Pending client reply to provide loan samples | 2021-10-16
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 | 2022-01-18 | 2022-02-28 | 40 | 2022-02-11 | YET TO START |  | 2022-01-24
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | PENDING DOCS | - Samples (TOC and revenue) sent to client - Fieldwork on 11 and 12 November 2021 to vouch on expenses and other income, TOC and revenue | 2021-09-14
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | HAO YAN, PIK EN TOH | 2021-12-31 |  |  | 40 | 2021-12-31 | PENDING DOCS | - Samples sent to client to prepare for Q1 - Q3 - Fieldwork on 11 and 12 November 2021 to vouch | 2021-10-16
BAN KING CREDIT (S) PTE. LTD. |  | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 | 2022-01-18 | 2022-02-28 | 32 | 2022-01-25 | REVIEWING - PARTNER | Send for partner review @ 25/1/22 | 2022-01-24
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | ZHEN KANG LAU, JUN LOKE, PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | Interim audit (for the period from 1/1/2021 - 30/9/2021 completed) Interim billing paid (S$2400) | 2021-09-15
BLISS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Interim AUP (Q1, Q2, and Q3) completed AUP fee billed for 3 quarters paid (S$1500) | 2021-09-28
BLISS CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-10 | 2022-02-28 | 32 | 2022-01-21 | REVIEWING - PARTNER |  | 2022-01-20
BRILLIANCE ALPHA ASSET MANAGEMENT PTE LTD | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | JIA XIAN FOONG, PIK EN TOH | 2021-09-30 | 2021-10-22 | 2022-01-31 | 80 | 2021-12-15 | REVIEWING - MANAGER |  | 2021-10-26
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | JUN LOKE, PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Roll forward AWP and audit programme - completed on 29/10.2021 | 2021-09-20
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | EMILY GOH, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) | 2021-09-27
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 | 2022-01-14 | 2022-02-28 | 40 | 2022-02-04 | REVIEWING - PARTNER |  | 2022-01-24
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Interim audit done. Updated on 09.12 | 2021-09-15
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP). Received softcopies for selected contracts. Overall contract checked. only few need to get additional supporting from client. Updated 0n 14.10 | 2021-10-24
CASHMAX CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 |  | 2022-02-28 | 40 | 2022-02-16 | REVIEWING - MANAGER | Email follow up on 2/2/22, 7/2/22 & 14/2/22 | 2022-01-27
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | YU XUEN NG | 2019-12-31 | 2020-10-12 | 2020-11-30 | 60 | 2021-11-30 | PENDING DOCS | 2. Follow up on 24/11/21 1. Pending signing doc. Follow up on 23/8 | 2020-10-29
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2020-12-31 |  |  | 60 | 2021-11-19 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
CHUNG TING FAI & CO | SYA PAC | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 24 | 2022-02-14 | REVIEWING - MANAGER | LOR received | 2022-01-19
CONTINENTAL LAW LLP - MR CHANG | SYA PAC | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 16 | 2022-02-14 | ACCOUNT NOT IN |  | 2022-01-19
CONTINENTAL LAW LLP - MR EDWARD | SYA PAC | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 8 | 2022-02-14 | ACCOUNT NOT IN |  | 2022-01-19
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | PIK EN TOH, JUN LOKE, WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | To accompany Vicky go fieldwork only Rollover and audit program - completed on 10/11/2021 | 2021-09-21
CREDIT 89 (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | PIK EN TOH, WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Quarter 1 and quarter 2 (interim AUP) | 2021-10-16
CREDIT 89 (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-19 | 2022-02-28 | 40 | 2022-02-16 | REVIEWING - PARTNER |  | 2022-01-27
CREDIT XTRA PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITHOUT ACCOUNT | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-17
CREDIT XTRA PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | WEI QI YU, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - MANAGER | Quarter 1 and quarter 2 (interim AUP) 1.) Completed AWP AUP | 2021-10-12
CREDIT XTRA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-18 | 2022-02-28 | 40 | 2022-01-28 | WIP |  | 2022-01-27
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | Roll forward AWP and audit programme; Done for AWP and audit program | 2021-09-17
FORTUNE CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Client sent in softcopy Quarter 1 and quarter 2 (interim AUP); AUP done @ 4/10/21 | 2021-10-12
FORTUNE CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-18 | 2022-02-28 | 40 | 2022-02-11 | REVIEWING - PARTNER |  | 2022-01-27
FULLERTON LAW CHAMBERS LLC | ACUMEN ASSURANCE | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 24 | 2022-02-14 | PLANNING WITH ACCOUNT | LOR received | 2022-01-19
HDR PAYMENTS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 |  |  | 80 | 2021-11-19 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
HDR SG PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | EMILY GOH | JING HE TAN, EMILY GOH | 2021-12-31 |  |  | 16 | 2021-12-31 | ACCOUNT NOT IN | roll over + audit program completed on 16/11/2021 | 2021-11-01
HHL CREDIT PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH |  |  |  | 24 | 2021-08-31 | FINALIZING | To print working paper and submit to partner | 2020-08-20
KANDIDATA ASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 | 2022-02-15 | 2022-03-18 | 80 | 2022-03-18 | WIP | 2. Vicky to commence the statutory audit 1. Hao Yan Roll forward for awp and audit program done | 2021-11-10
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | HAO YAN, SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 80 | 2022-03-31 | REVIEWING - TEAM LEAD | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.)In progress the roll over the audit program | 2021-09-21
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | JUN LOKE, HAO YAN, SHARON WONG, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-12-31 | REVIEWING - TEAM LEAD | Sent in softcopy, assigned to Hao Yan Quarter 1 and quarter 2 (interim AUP); AUP done @ 4/10/21; AUP Q3 done 21/10/21 | 2021-10-08
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-12 | 2022-02-28 | 40 | 2022-01-25 | REVIEWING - PARTNER |  | 2022-01-24
LOH BROTHERS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | WEI QI YU, EMILY GOH, HAO YAN | 2021-03-31 | 2021-10-25 |  | 80 | 2022-01-31 | KIV | Roll forward for awp and audit program done | 2021-11-10
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | JUN LOKE, HAO YAN, EMILY GOH, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Interim audit done. Updated on 09.12 | 2021-09-22
MAGNUS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP). Client is preparing selected samples and will inform once is ready Updated on 07.10.; AUP Q1Q2 done | 2021-10-11
MAGNUS CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | PATSY LEE | PATSY LEE | 2021-12-31 |  | 2022-02-28 | 40 | 2022-02-18 | ACCOUNT NOT IN |  | 2022-01-27
NOVOTEC EDM SUPPLIES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JIA XIAN FOONG | JIA XIAN FOONG | 2021-12-31 |  |  | 80 | 2021-11-19 | ACCOUNT NOT IN | Roll forward of AWP | 2021-11-09
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | WIP | Account not in. Reminded client on 02.12. Account received on 03.01.2022 Updated on 20.01 | 2021-09-22
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | JUN LOKE, HAO YAN, YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP); AUP Q1Q2 done | 2021-10-11
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 |  | 2022-02-28 | 40 | 2022-02-22 | PENDING DOCS |  | 2022-01-27
PETER ONG LAW CORPORATION | SYA PAC | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 24 | 2022-02-14 | ACCOUNT NOT IN |  | 2022-01-19
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Interim audit done, only pending vouching of invoices. | 2021-09-23
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP). Sample selection sent, awaiting client to prepare. Updated on 28.10. | 2021-10-20
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 |  | 2022-02-28 | 40 | 2022-02-25 | PENDING DOCS | Email follow up on 28/1/22, 7/2/22 & 14/2/22. | 2022-01-27
PROCESS TECHNOLOGY CONSULTANTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | WEI QI YU, XUN HUI SOH | 2021-03-31 | 2021-06-09 | 2021-09-30 | 60 | 2021-10-29 | PENDING PAYMENT | 1. Account received on 9 June 2021 | 2021-06-25
PY LEGAL LLC | ACUMEN ASSOCIATES LLP | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 24 | 2022-02-14 | REVIEWING - MANAGER | LOR received | 2022-01-19
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2022-03-31 | INTERIM COMPLETED | Interim AUP (Q1, Q2 and Q3) completed AUP fee for 3 quarters paid (S$1020) | 2021-09-24
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | PLANNING WITH ACCOUNT | Interim audit (for the period from 1/1/2021 - 30/9/2021) completed Interim billing paid (S$2550) | 2021-09-24
RAFFLES CREDIT PTE. LTD. |  | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 | 2022-01-18 | 2022-02-28 | 32 | 2022-01-25 | REVIEWING - PARTNER | Queries sent @ 26/1/22 | 2022-01-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | INTERIM COMPLETED | Roll forward AWP and audit programme; Done for AWP and audit program | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | INTERIM COMPLETED | Quarter 1 and quarter 2 (interim AUP) | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 | 2022-01-13 | 2022-02-28 | 32 | 2022-01-28 | WIP |  | 2022-01-24
SCDA ARCHITECTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JIA XIAN FOONG | JIA XIAN FOONG | 2021-12-31 |  |  | 80 | 2021-11-19 | ACCOUNT NOT IN | Roll forward of AWP | 2021-11-09
SCDA DESIGN PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2021-12-31 |  |  | 150 | 2021-11-19 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
SCDA INTERIORS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | EMILY GOH | ZHEN KANG LAU, EMILY GOH | 2021-12-31 |  |  | 16 | 2021-12-31 | ACCOUNT NOT IN | roll over | 2021-11-01
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | JING HE TAN, WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme - completed on 28/10/21 | 2021-09-27
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | EMILY GOH, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-12-31 | WIP | Quarter 1 and quarter 2 (interim AUP) | 2021-10-12
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-19 | 2022-02-28 | 40 | 2022-02-18 | REVIEWING - PARTNER |  | 2022-01-27
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 80 | 2022-03-31 | ACCOUNT NOT IN | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-27
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-10-04 | ACCOUNT NOT IN | Quarter 1 and quarter 2 (interim AUP) 1.) No interim AUP for SME care, no loan issue as at June 2021 | 2021-09-27
SME CARE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | IRENE TEO | IRENE TEO | 2021-12-31 |  | 2022-02-28 | 32 | 2022-02-18 | REVIEWING - MANAGER |  | 2022-01-24
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JIA XIAN FOONG | JIA XIAN FOONG | 2021-12-31 |  |  | 80 | 2021-11-19 | ACCOUNT NOT IN | Roll forward of AWP | 2021-11-09
SYNERGY LI CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2021-03-31 |  |  | 150 | 2021-11-19 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
SYNERGY LI INTERNATIONAL RESOURCES LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | EMILY GOH | EMILY GOH | 2021-03-31 |  |  | 16 | 2021-12-31 | ACCOUNT NOT IN | roll over | 2021-11-01
TECHNIDRILL AUSTRALASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, JIA XIAN FOONG | 2021-12-31 | 2022-01-10 | 2022-02-28 | 80 | 2022-02-28 | REVIEWING - MANAGER | Account received on 10 January 2022, assigned to Pui Shi. Jia Xian Roll forward of AWP | 2021-11-09
TOONG CHAI PRESBYTERIAN CHURCH | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU, HAO YAN | 2021-12-31 | 2022-01-17 | 2022-02-28 | 80 | 2022-02-28 | WIP | Account received on 17 January 2022. Roll forward for awp and audit program done | 2021-11-10
UNIQCASH PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG |  | 2021-02-22 | 2021-04-30 | 20 | 2021-05-31 | FINALIZING | PMFT report obtained. will schedule one day for wrapping up. | 2021-02-22
WILLIAM POH & LOUIS LIM | ACUMEN ASSOCIATES LLP | LAWYERS AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE | 2021-12-31 |  |  | 32 | 2022-02-14 | PLANNING WITH ACCOUNT |  | 2022-01-19