## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
ACESSE (M) SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | TZE KARN KONG | JIVAN SR | 2020-12-31 | 2021-10-22 | 2021-10-31 | 16 | 2021-10-31 | PENDING PAYMENT | submitted on 27/10/2021 | 2021-10-22
AGRI OILS PACKAGING SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-06-30 | 2021-11-22 | 2022-02-28 | 32 | 2021-12-31 | PENDING PAYMENT | submitted @ by 22-2-22 | 2021-11-23
ASIA PAYROLL & SERVICES SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-09-30 | 2022-03-07 | 2022-05-31 | 16 | 2022-03-25 | REVIEWING - TEAM LEAD | form c ehasil should be release by previous tax agent, form c drafted on 15/3/22 | 2022-03-11
ESL GAMING MALAYSIA SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-12-31 | 2022-02-28 | 2022-08-31 | 32 | 2022-03-14 | REVIEWING - TEAM LEAD | pending draft report to finalised form C, form c drafted on 7/3/22 | 2022-02-28
FIRST POINT GROUP LTD | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | STEFFI CHEAH | JIVAN SR | 2021-04-30 | 2021-11-01 | 2021-11-12 | 56 | 2021-11-09 | REVIEWING - MANAGER |  | 2021-11-01
FIRST POINT GROUP LTD | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-04-30 | 2021-11-08 | 2022-01-31 | 40 | 2022-02-15 | REVIEWING - MANAGER | Kenny review @15-3-22 | 2022-01-20
HERMAN CORPORATE ADVISORY SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | TZE KARN KONG | JIVAN SR | 2020-12-31 | 2021-10-22 | 2021-10-31 | 40 | 2021-05-17 | PENDING PAYMENT | submitted on 28/10/2021 | 2021-10-22
HHL CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | HWEE XIN LIM | EMILY GOH | JIVAN SR, EMILY GOH | 2021-12-31 |  |  | 40 | 2022-02-28 | PENDING PAYMENT | sent for Mr. Woelly review on 25/2/2022, pass to audit on 4/3/22 | 2022-02-16
KARTHIK MONEY LENDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | PAI NEE WONG | JIVAN SR | JIVAN SR | 2021-12-31 | 2022-01-12 | 2022-02-28 | 25 | 2022-01-21 | PENDING PAYMENT | sent for Mr. Looi review on 21st Jan, done review by Mr. Looi on 25th Jan. Review done by Mr. Woelly and procced to audit on 11/2 | 2022-01-12
KYROX SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, LOK YEE RENNIE THEW | 2020-05-30 | 2021-09-17 | 2021-10-31 | 12 | 2021-09-30 | PENDING PAYMENT | proceed submission @ 26-10-21 | 2021-09-17
MYPOST HOLDING SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2020-12-31 | 2021-10-01 | 2021-10-29 | 16 | 2021-10-29 | PENDING PAYMENT | submitted @27-10-21 | 2021-10-18
OPTIMIMED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LIM NIAW YUN | YI LING CHOO | LOK YEE RENNIE THEW | JIVAN SR, SHANNIE SHANNIE | 2021-09-30 | 2021-11-16 | 2021-11-19 | 50 | 2021-11-19 | SENT OUT FOR ADOPTION | acct finalised ; compile @ 23-2-22 | 2021-11-16
OPTIMIMED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LIM NIAW YUN | YI LING CHOO | LOK YEE RENNIE THEW | JIVAN SR, STEFFI CHEAH, SHANNIE SHANNIE | 2021-09-30 | 2021-11-16 | 2021-11-19 | 60 | 2021-11-19 | PENDING PAYMENT | Approved @ 23-2-22; pending compile | 2021-11-16
OPTIMIMED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LIM NIAW YUN | YI LING CHOO | LOK YEE RENNIE THEW | JIVAN SR, SHANNIE SHANNIE | 2021-09-30 | 2021-11-16 | 2021-11-19 | 50 | 2021-11-19 | SENT OUT FOR ADOPTION |  | 2021-11-16
OT CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | HWEE XIN LIM | JIVAN SR | JIVAN SR | 2021-12-31 |  |  | 40 | 2022-02-28 | PENDING PAYMENT | sent for Mr. Woelly review on 25/2/2022, pass to audit on 1/3/2022 | 2022-02-16
PERIAKARUPPAN CHETTIAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | PAI NEE WONG | JIVAN SR | JIVAN SR | 2021-12-31 | 2022-01-08 | 2022-02-28 | 16 | 2022-01-21 | PENDING PAYMENT | sent for client review on 21st Jan, client ok to proceed on 26th Jan, review done by Mr. Woelly and procced to audit on 11/2 | 2022-01-08
S.P. MEGA - MARIHARTA SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-07-31 | 2022-01-26 | 2022-02-13 | 16 | 2022-02-11 | REVIEWING - PARTNER | Simon review 25-2-22 | 2022-01-26
SIGHAPPI ACHI MONEYLENDER (SG) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | PAI NEE WONG | JIVAN SR | JIVAN SR | 2021-12-31 | 2022-01-11 | 2022-02-28 | 16 | 2022-01-21 | PENDING PAYMENT | sent for client review on 21st Jan, client ok to proceed on 25th Jan, review done by Mr. Woelly and procced to audit on 14/2 | 2022-01-11
SOHO LIVING GROUP SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, STEFFI CHEAH | 2021-06-30 | 2021-11-19 | 2021-11-30 | 40 | 2021-11-30 | SENT OUT FOR ADOPTION | signing to chengco @ 7-3-22 | 2021-11-19
SOHO LIVING GROUP SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, STEFFI CHEAH | 2021-06-30 | 2021-11-19 | 2021-11-30 | 40 | 2021-11-30 | PENDING PAYMENT | submitted @ 25-2-22 | 2021-11-19
TET GLOBAL HOLDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-12-31 | 2022-01-24 | 2022-02-28 | 72 | 2022-02-18 | REVIEWING - MANAGER | For team lead review at 14/2. For Mr. Ray review at 16/2, sent for client review on 3/3/22 | 2022-01-24
TET GLOBAL HOLDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-12-31 | 2022-02-07 | 2022-04-30 | 16 | 2022-02-18 | REVIEWING - MANAGER | sent for client review on 3/3/22 | 2022-01-24
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, LOK YEE RENNIE THEW | 2020-05-31 | 2021-09-13 | 2021-11-30 | 72 | 2021-09-22 | REVIEWING - PARTNER | Chengco @ 16-11-21 | 2021-09-13
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, LOK YEE RENNIE THEW | 2020-05-31 | 2021-09-16 | 2021-11-30 | 10 | 2021-09-26 | REVIEWING - PARTNER | Mr Simon review @30-11-21 | 2021-09-16
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-05-31 | 2021-11-29 | 2021-12-31 | 56 | 2021-12-31 | REVIEWING - PARTNER | submitted to team lead review on 10.12.2021; To amend accordingly @13/12/21; Submitted for Mr. Ray review on 14/12/21 | 2021-11-29
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-05-31 | 2021-12-02 | 2021-12-31 | 24 | 2021-12-31 | REVIEWING - MANAGER | submitted for Mr. Ray review on 14/12/21 | 2021-12-02