## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
ACUMEN ALPHA TAXATION SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | JING HE TAN | 2021-09-30 | 2021-12-15 | 2022-01-31 | 60 | 2022-01-31 | REVIEWING - PARTNER |  | 2022-01-25
ACUMEN ALPHA TAXATION SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | TAXATION | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | JING HE TAN | 2021-09-30 | 2021-12-15 | 2022-01-31 | 16 | 2022-02-08 | REVIEWING - PARTNER |  | 2022-01-25
ADVANCE CASH CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2021-12-31 | 2022-01-25 | 2022-01-28 | 40 | 2022-01-28 | PENDING PAYMENT | Sent out for adoption @ 21-1-2022 | 2022-01-25
ADVANCE CASH CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | HWEE XIN LIM | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2021-12-31 |  | 2022-02-28 | 40 | 2022-01-21 | PENDING PAYMENT | proceed for audit @ 11-2-22 | 2022-01-10
BSL 5220 SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2020-12-31 | 2021-06-01 | 2021-07-30 | 32 | 2021-07-12 | PENDING PAYMENT | lodge @ 5-11-21 | 2021-06-16
BSL 5220 SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2020-12-31 | 2021-09-01 | 2021-09-30 | 16 | 2021-09-16 | PENDING PAYMENT | submitted @25-10-21 | 2021-09-02
BSL 5220 SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHENG JIE HENG | 2021-12-31 | 2022-02-16 | 2022-03-31 | 48 | 2022-03-31 | REVIEWING - PARTNER |  | 2022-02-23
BSL 5220 SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHENG JIE HENG | 2021-12-31 | 2022-02-23 | 2022-03-31 | 16 | 2022-03-31 | REVIEWING - PARTNER |  | 2022-02-23
CARBI-DECO LEATHER INDUSTRY SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | ZHEN KANG LAU, LOK YEE RENNIE THEW | 2020-12-31 | 2021-06-16 | 2021-11-30 | 40 | 2021-09-30 | PENDING PAYMENT | lodged and sent to client @ 31-12-21 | 2021-06-16
CARBI-DECO LEATHER INDUSTRY SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHEN KANG LAU, LOK YEE RENNIE THEW | 2020-12-31 | 2021-09-25 | 2021-10-31 | 16 | 2021-10-11 | PENDING PAYMENT | submitted @ 29-10-21 | 2021-09-28
CD SEAT INDUSTRIES SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | ZHEN KANG LAU, SHANNIE SHANNIE | 2020-12-31 | 2021-09-24 | 2021-10-11 | 80 | 2021-10-11 | PENDING PAYMENT | report obtained, lodged, sent to client @ 31-12-21 | 2021-09-27
CD SEAT INDUSTRIES SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHEN KANG LAU, SHANNIE SHANNIE | 2020-12-31 | 2021-09-24 | 2021-10-31 | 16 | 2021-10-15 | PENDING PAYMENT |  | 2021-09-27
CRAVINGS CURATORS SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | ANDY, HSL | TZE KARN KONG | LOK YEE RENNIE THEW | SHANNIE SHANNIE, KWEH CHUN SHENG | 2020-12-31 | 2021-08-16 | 2021-10-13 | 64 | 2021-08-31 | PENDING PAYMENT | lodged @ 10-1-21 | 2021-08-18
CRAVINGS CURATORS SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | SHANNIE SHANNIE, ZHEN KANG LAU | 2020-12-31 | 2021-08-16 | 2021-10-20 | 16 | 2021-09-05 | PENDING PAYMENT | submitted @ 3-1-21 | 2021-10-22
DAS INNOVATE SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | EMILY GOH | LOK YEE RENNIE THEW, JUN LOKE, JIA XIAN FOONG | 2020-12-31 | 2021-08-30 | 2021-09-10 | 16 | 2021-09-10 | PENDING PAYMENT | submitted @ 27-10-21 | 2021-10-22
ENERGE ASIA PTE. LTD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, JING HE TAN | 2021-06-30 | 2022-03-08 | 2022-04-30 | 150 | 2022-03-31 | REVIEWING - MANAGER | SA review @ 4-4-2022 Draft approved by client @ 6-4-22 | 2022-03-14
ESL GAMING MALAYSIA SDN BHD | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | BRIAN LEE | 2021-12-31 | 2022-02-16 | 2022-03-11 | 120 | 2022-02-28 | REVIEWING - PARTNER | Send out for adoption @ 20-3-22 Mr Ray review @ 11-3-22 sent to Ian @4-3-22 | 2022-02-17
ESL GAMING MALAYSIA SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-12-31 | 2022-02-28 | 2022-08-31 | 32 | 2022-03-14 | REVIEWING - MANAGER | pending draft report to finalised form C, form c drafted on 7/3/22 | 2022-02-28
FINE DINERS SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | ANDY, HSL | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2020-12-31 | 2021-08-01 | 2021-09-30 | 40 | 2021-09-30 | PENDING PAYMENT | lodge to SSM @ 27-10-21 | 2021-08-09
FINE DINERS SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2020-12-31 | 2021-08-23 | 2021-10-31 | 16 | 2021-09-15 | PENDING PAYMENT | submitted @ 28-10-21 | 2021-09-01
FOOD CURATORS SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | ANDY, HSL | TZE KARN KONG | LOK YEE RENNIE THEW | SHANNIE SHANNIE | 2020-12-31 | 2021-08-16 | 2021-08-31 | 64 | 2021-09-30 | PENDING PAYMENT | lodged @ 10-1-21 | 2021-08-18
FOOD CURATORS SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | SHANNIE SHANNIE | 2020-12-31 | 2021-08-16 | 2021-09-05 | 16 | 2021-09-05 | PENDING PAYMENT | Submitted @ 3-1-2022 | 2021-08-18
GAYAREKA HOMES & GARDENS SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | ANDY, HSL | TZE KARN KONG | LOK YEE RENNIE THEW | SHANNIE SHANNIE | 2020-12-31 | 2021-08-16 | 2021-09-05 | 40 | 2021-09-30 | PENDING PAYMENT | lodged @ 10-1-21 | 2021-08-17
GAYAREKA HOMES & GARDENS SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JING HE TAN, SHANNIE SHANNIE | 2020-12-31 | 2021-08-16 | 2021-09-05 | 16 | 2021-09-05 | PENDING PAYMENT | submitted form C @ 26.10.21 | 2021-08-24
GOH CHEE KIANG | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2021-12-31 | 2022-04-04 | 2022-04-30 | 10 | 2022-04-12 | WIP |  | 2022-04-05
KAZHOU PTE. LTD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | AARON TSEN, JIVAN SR | 2021-12-31 | 2022-04-01 | 2022-04-30 | 96 | 2022-04-30 | WIP | first draft submitted on 08/04/22 | 2022-04-04
KYROX SDN BHD | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2020-05-30 | 2021-08-01 | 2020-09-30 | 5 | 2021-09-30 | PENDING PAYMENT | lodged @ 2-12-21 | 2021-09-17
KYROX SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, LOK YEE RENNIE THEW | 2020-05-30 | 2021-09-17 | 2021-10-31 | 12 | 2021-09-30 | PENDING PAYMENT | proceed submission @ 26-10-21 | 2021-09-17
KYROX SDN BHD | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JING HE TAN | 2021-05-31 | 2022-01-07 | 2022-01-31 | 80 | 2022-01-31 | REVIEWING - PARTNER | pending account functional currency change from MYR to SGD from account department.@ 24-1-22 | 2022-01-07
KYROX SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JING HE TAN | 2021-05-31 | 2022-01-14 | 2022-01-31 | 16 | 2022-01-31 | REVIEWING - PARTNER |  | 2022-01-14
M&E CAPITAL GROUP SDN BHD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | LOK YEE RENNIE THEW | 2020-12-31 | 2021-09-01 | 2021-09-30 | 4 | 2021-09-15 | PENDING PAYMENT | submitted @25-10-21 | 2021-09-07
MARQUX SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | SHANNIE SHANNIE | 2020-05-31 | 2021-11-23 | 2022-01-31 | 30 | 2022-01-07 | REVIEWING - PARTNER | submit to chengco @ 16-12-21 | 2021-12-13
MARQUX SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHEN KANG LAU | 2020-05-31 | 2021-12-16 | 2022-01-31 | 16 | 2022-01-31 | REVIEWING - PARTNER | pending report finalised @ 21-12-21 | 2021-12-20
MARQUX SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHENG JIE HENG | 2021-05-31 | 2022-02-23 | 2022-02-28 | 24 | 2022-02-28 | PENDING DOCS |  | 2022-02-23
MARQUX SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHENG JIE HENG | 2021-05-31 | 2022-02-23 | 2022-02-28 | 8 | 2022-02-28 | PENDING DOCS |  | 2022-02-23
MYPOST HOLDING SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2020-12-31 | 2021-10-01 | 2021-10-29 | 16 | 2021-10-29 | PENDING PAYMENT | submitted @27-10-21 | 2021-10-18
MYPOZ BERHAD | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JING HE TAN | 2020-12-31 | 2021-10-01 | 2021-10-31 | 16 | 2021-10-25 | PENDING PAYMENT | submitted @27-10-21 | 2021-10-18
OPTIMIMED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LIM NIAW YUN | YI LING CHOO | LOK YEE RENNIE THEW | JIVAN SR, SHANNIE SHANNIE | 2021-09-30 | 2021-11-16 | 2021-11-19 | 50 | 2021-11-19 | SENT OUT FOR ADOPTION | acct finalised ; compile @ 23-2-22 | 2021-11-16
OPTIMIMED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LIM NIAW YUN | YI LING CHOO | LOK YEE RENNIE THEW | JIVAN SR, STEFFI CHEAH, SHANNIE SHANNIE | 2021-09-30 | 2021-11-16 | 2021-11-19 | 60 | 2021-11-19 | PENDING PAYMENT | Approved @ 23-2-22; pending compile | 2021-11-16
OPTIMIMED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LIM NIAW YUN | YI LING CHOO | LOK YEE RENNIE THEW | JIVAN SR, SHANNIE SHANNIE | 2021-09-30 | 2021-11-16 | 2021-11-19 | 50 | 2021-11-19 | SENT OUT FOR ADOPTION |  | 2021-11-16
QHFOXX PTE. LTD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | ZHENG JIE HENG, BRIAN LEE | 2021-12-31 | 2022-04-01 | 2022-04-30 | 104 | 2022-04-30 | WIP |  | 2022-04-05
SOHO LIVING GROUP SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, STEFFI CHEAH | 2021-06-30 | 2021-11-19 | 2021-11-30 | 40 | 2021-11-30 | PENDING PAYMENT | signing to chengco @ 7-3-22 | 2021-11-19
SOHO LIVING GROUP SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, STEFFI CHEAH | 2021-06-30 | 2021-11-19 | 2021-11-30 | 40 | 2021-11-30 | PENDING PAYMENT | submitted @ 25-2-22 | 2021-11-19
SUMBANGAN LAGENDA SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | CHIN VOON TEE | LOK YEE RENNIE THEW | 2021-06-30 |  |  | 80 | 2021-08-16 | PENDING PAYMENT | signing sent to chengco @ 27-10-21 | 2021-07-26
TET GLOBAL HOLDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-12-31 | 2022-01-24 | 2022-02-28 | 72 | 2022-02-18 | SENT OUT FOR ADOPTION | For team lead review at 14/2. For Mr. Ray review at 16/2, sent for client review on 3/3/22, pending approval from client. Received amendments from Josephine on 28/3. Josephine 2nd review on 12/4 | 2022-01-24
TET GLOBAL HOLDING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-12-31 | 2022-02-07 | 2022-04-30 | 16 | 2022-02-18 | SENT OUT FOR ADOPTION | sent for client review on 3/3/22,pending approval from client. Received amendments from Josephine on 28/3. Josephine 2nd review on 12/4 | 2022-01-24
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, LOK YEE RENNIE THEW | 2020-05-31 | 2021-09-13 | 2021-11-30 | 72 | 2021-09-22 | REVIEWING - PARTNER | Chengco @ 16-11-21 | 2021-09-13
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR, LOK YEE RENNIE THEW | 2020-05-31 | 2021-09-16 | 2021-11-30 | 10 | 2021-09-26 | REVIEWING - PARTNER | Mr Simon review @30-11-21 | 2021-09-16
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | CHENGCO PLT | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-05-31 | 2021-11-29 | 2021-12-31 | 56 | 2021-12-31 | REVIEWING - PARTNER | submitted to team lead review on 10.12.2021; To amend accordingly @13/12/21; Submitted for Mr. Ray review on 14/12/21 | 2021-11-29
THE REGENATIVE CLINIC SDN. BHD. | ACUMEN ALPHA TAXATION SDN BHD | TAXATION | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | JIVAN SR | 2021-05-31 | 2021-12-02 | 2021-12-31 | 24 | 2021-12-31 | REVIEWING - MANAGER | submitted for Mr. Ray review on 14/12/21 | 2021-12-02
WESTHEAD MEDIA LIMITED | ACUMEN ALPHA ADVISORY SDN BHD | STATUTORY AUDIT | RAY KONG | TZE KARN KONG | LOK YEE RENNIE THEW | HAO YAN, JUN LOKE, JING HE TAN | 2020-12-31 | 2021-11-01 | 2021-11-12 | 48 | 2021-11-08 | REVIEWING - PARTNER | 16-3-22 Kenny review | 2021-11-01