## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
3 THIRTY NINE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 30 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
3 THIRTY NINE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 30 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
3 THIRTY NINE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 30 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
529 INVESTMENTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-02-15 | 2022-06-30 | 35 | 2022-03-15 | REVIEWING - MANAGER |  | 2022-03-01
529 INVESTMENTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-02-15 | 2022-06-30 | 35 | 2022-03-15 | REVIEWING - MANAGER |  | 2022-03-01
529 INVESTMENTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-02-15 | 2022-06-30 | 35 | 2022-03-15 | REVIEWING - MANAGER |  | 2022-03-01
777 INTERNATIONAL TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 10 | 2022-04-12 | ACCOUNT NOT IN |  | 2022-04-11
777 INTERNATIONAL TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 10 | 2022-04-12 | ACCOUNT NOT IN |  | 2022-04-11
88 GARAGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 |  | 2021-11-30 | 8 | 2021-07-16 | KIV |  | 2021-06-08
ACUMEN NOVELTY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | XBRL PREPARATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-08-31 | 2021-10-21 | 2022-02-28 | 25 | 2021-11-23 | REVIEWING - PARTNER |  | 2021-11-15
ALTO FABRIC PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-06-30 | 2021-12-09 | 2021-12-31 | 20 | 2022-01-31 | REVIEWING - MANAGER |  | 2022-01-04
ARENA RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-08 | WIP |  | 2022-04-04
ARENA RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-08 | WIP |  | 2022-04-04
ARENA RECOVERY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-08 | ACCOUNT NOT IN |  | 2022-04-04
ASIA RED PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-05-31 | 2021-11-30 | 2021-11-30 | 30 | 2021-12-31 | REVIEWING - MANAGER |  | 2021-12-01
AUTOCOUNT (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-12-31 |  |  | 25 | 2022-01-28 | ACCOUNT NOT IN |  | 2022-01-24
AVIS MANAGEMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | STRIKING OFF | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-10-31 | 2021-12-01 | 2021-12-31 | 5 | 2021-12-31 | PENDING DOCS |  | 2021-12-01
BLUELAMBDA PRIVATE LIMITED | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-10-29 | 2021-12-31 | 20 | 2021-11-30 | INTERIM COMPLETED |  | 2021-11-01
BRAVOS COLLECTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-09-30 | 2021-12-09 | 2022-03-31 | 20 | 2022-01-07 | PLANNING WITH ACCOUNT |  | 2021-12-20
BRAVOS COLLECTION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-09-30 | 2021-12-09 | 2022-03-31 | 20 | 2022-01-07 | REVIEWING - MANAGER |  | 2021-12-20
BUYNASIAN SUPPLY CHAIN PARTNERS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-07-31 | 2021-11-16 | 2022-01-31 | 15 | 2021-12-10 | REVIEWING - MANAGER |  | 2021-12-01
BUYNASIAN SUPPLY CHAIN PARTNERS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-07-31 | 2021-11-16 | 2022-01-31 | 15 | 2021-12-10 | REVIEWING - MANAGER |  | 2021-12-01
CARWORKZ | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-15 | 2022-03-31 | 14 | 2022-03-15 | WIP | 4-LINE STATEMENT | 2022-03-01
CARWORKZ | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-15 | 2022-03-31 | 14 | 2022-03-15 | WIP | 4-LINE STATEMENT | 2022-03-01
CARWORKZ SG PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-03-15 | 2022-06-30 | 40 | 2022-03-31 | ACCOUNT NOT IN | Include accounting | 2022-03-01
CHERYL W PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-09-30 | 2021-12-15 | 2022-03-31 | 15 | 2022-01-21 | SENT OUT FOR ADOPTION |  | 2022-01-10
CHERYL W PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-09-30 | 2021-12-15 | 2022-03-31 | 15 | 2022-01-21 | SENT OUT FOR ADOPTION |  | 2022-01-10
CLINICAL ART (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-22 | REVIEWING - MANAGER |  | 2022-04-11
CLINICAL ART (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-22 | REVIEWING - MANAGER |  | 2022-04-11
CLINICAL ART (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2021-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-22 | PLANNING COMPLETED - WITH ACCOUNT |  | 2022-04-11
CRAWFORT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YEE TING GWEE | YI LING CHOO | POH YEN LWI | 2020-12-31 | 2021-08-13 | 2021-11-30 | 24 | 2021-09-10 | SENT OUT FOR ADOPTION | Pending for group relief | 2021-01-11
DUSCHE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2020-02-29 |  | 2020-08-31 | 8 | 2020-12-18 | ACCOUNT NOT IN | Yearly acctg, compilation FS & income tax computation After payment only commence job | 2020-04-01
DYSON DEVELOPMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2022-09-30 | 2022-02-14 | 2022-02-28 | 10 | 2022-02-28 | ACCOUNT NOT IN |  | 2022-02-21
DYSON DEVELOPMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2022-09-30 | 2022-02-14 | 2022-02-28 | 10 | 2022-02-28 | ACCOUNT NOT IN |  | 2022-02-21
DYSON DEVELOPMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | STRIKING OFF | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2022-09-30 | 2022-02-14 | 2022-02-28 | 10 | 2022-02-28 | ACCOUNT NOT IN |  | 2022-02-21
EIGHTYTWO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2022-06-30 | 2022-03-02 | 2022-03-31 | 32 | 2022-03-31 | ACCOUNT NOT IN |  | 2022-03-01
EKI TELECOMMUNICATIONS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-08-31 | 2021-10-21 | 2022-02-28 | 20 | 2021-11-12 | REVIEWING - MANAGER |  | 2021-11-01
EKI TELECOMMUNICATIONS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-08-31 | 2021-10-21 | 2022-02-28 | 20 | 2021-11-12 | REVIEWING - MANAGER |  | 2021-11-01
EMVERTEX CAPITAL | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-12-31 | 2022-04-11 | 2022-04-18 | 4 | 2022-04-12 | PENDING DOCS |  | 2022-04-12
EVERLUMIERE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-17 | 2022-02-17 | 14 | 2022-03-16 | SENT OUT FOR ADOPTION |  | 2022-03-14
EVERLUMIERE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-17 | 2022-02-17 | 14 | 2022-03-16 | SENT OUT FOR ADOPTION |  | 2022-03-14
FLORA MOMENTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-14 | 2022-06-30 | 32 | 2022-04-22 | ACCOUNT NOT IN |  | 2022-04-18
FLORA MOMENTS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-14 | 2022-06-30 | 32 | 2022-04-22 | ACCOUNT NOT IN |  | 2022-04-18
GENESIS MIND PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-07-31 | 2021-10-21 | 2022-01-31 | 25 | 2021-11-19 | KIV | Pending E-file YA2022 | 2021-11-15
GLAM INVESTMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | GST REGISTRATION APPLICATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2023-01-31 | 2022-04-01 |  | 3 | 2022-03-11 | ACCOUNT NOT IN |  | 2022-03-01
GOAL ARENA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING |  | 2022-03-09 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-21
GOAL ARENA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING |  | 2022-03-09 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-21
GOAL ARENA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING |  | 2022-03-09 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-21
GRINTEC ENGINEERING PRIVATE LIMITED | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-04-30 | 2021-08-03 | 2021-10-31 | 40 | 2021-09-30 | SENT OUT FOR ADOPTION | PENDING FOR CLIENT REPLY ON PROJECT COSTING WORKSHEET | 2021-09-01
HALCYON CAPITAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-02-25 | 2022-06-30 | 10 | 2022-03-03 | SENT OUT FOR ADOPTION |  | 2022-03-01
HALCYON CAPITAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-02-25 | 2022-06-30 | 10 | 2022-03-03 | SENT OUT FOR ADOPTION |  | 2022-03-01
HEALTH CAPITAL (PUNGGOL OASIS) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2020-01-31 | 2022-02-17 | 2022-03-31 | 28 | 2022-03-18 | ACCOUNT NOT IN |  | 2022-03-14
HEALTH CAPITAL (PUNGGOL OASIS) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2020-01-31 | 2022-02-17 | 2022-03-31 | 28 | 2022-03-18 | ACCOUNT NOT IN |  | 2022-03-14
HEALTH CAPITAL (SENGKANG CENTRAL) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2019-11-30 | 2021-12-15 | 2022-05-31 | 25 | 2022-01-31 | ACCOUNT NOT IN |  | 2022-01-10
HEALTH CAPITAL (SENGKANG CENTRAL) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2019-11-30 | 2021-12-15 | 2022-05-31 | 25 | 2022-01-31 | ACCOUNT NOT IN |  | 2022-01-10
HERMAN ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-06-30 | 2021-12-07 | 2021-12-31 | 15 | 2021-12-17 | PENDING PAYMENT |  | 2021-12-13
HERMAN ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-06-30 | 2021-12-07 | 2021-12-31 | 15 | 2021-12-17 | SENT OUT FOR ADOPTION |  | 2021-12-13
HK150 CONNOISSEUR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | BRIAN LEE, HUI LING PANG | 2021-07-31 | 2021-10-21 | 2022-01-31 | 20 | 2021-11-26 | FINALIZING |  | 2021-11-15
HK150 CONNOISSEUR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | BRIAN LEE, HUI LING PANG | 2021-07-31 | 2021-10-21 | 2022-01-31 | 20 | 2021-11-26 | FINALIZING |  | 2021-11-15
HUAMALL CEMENT TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-02-16 | 2022-06-30 | 16 | 2022-03-04 | REVIEWING - MANAGER |  | 2022-03-01
HUAMALL CEMENT TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-02-16 | 2022-06-30 | 16 | 2022-03-04 | REVIEWING - MANAGER |  | 2022-03-01
I3 ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN |  | 2022-02-15 | 2022-05-31 | 32 | 2022-03-15 | YET TO START |  | 2022-03-01
I3 ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN |  | 2022-02-15 | 2022-05-31 | 32 | 2022-03-15 | YET TO START |  | 2022-03-01
I3 ADVISORY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN |  | 2022-02-15 | 2022-05-31 | 32 | 2022-03-15 | YET TO START |  | 2022-03-01
ICHILD COMPANY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-08-31 | 2021-10-21 | 2022-02-28 | 35 | 2021-11-12 | REVIEWING - MANAGER |  | 2021-11-01
ICHILD COMPANY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-08-31 | 2021-10-21 | 2022-02-28 | 35 | 2021-11-12 | REVIEWING - MANAGER |  | 2021-11-01
ICHILD COMPANY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-08-31 | 2021-10-21 | 2022-02-28 | 35 | 2021-11-12 | REVIEWING - MANAGER |  | 2021-11-01
IDEALBIZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-18 | 2022-06-30 | 32 | 2022-03-25 | REVIEWING - MANAGER |  | 2022-03-21
IDEALBIZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-18 | 2022-06-30 | 32 | 2022-03-25 | REVIEWING - MANAGER | PENDING QUERIES | 2022-03-21
IDEALBIZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-02-18 | 2022-06-30 | 32 | 2022-03-25 | REVIEWING - MANAGER |  | 2022-03-21
IDREGO ACE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | WOELLY WILLIAM | YI LING CHOO | POH YEN LWI | TIAN LEI TONG | 2021-09-30 | 2021-10-15 | 2021-10-22 | 4 | 2021-10-18 | PENDING PAYMENT | sent to yi ling review on 29/10.21-temporary as review point status due to sept'21 timesheet issue no settle yet | 2021-10-18
INFORMA SOLUTIONS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2020-07-31 | 2021-11-29 | 2021-12-31 | 25 | 2021-12-31 | SENT OUT FOR ADOPTION |  | 2021-12-01
JD CREDIT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2019-12-31 | 2022-02-08 | 2022-01-31 | 30 | 2022-02-11 | INTERIM COMPLETED |  | 2022-02-08
JLT BUGIS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-12-31 | 2022-03-16 | 2022-06-30 | 32 | 2022-04-22 | ACCOUNT NOT IN |  | 2022-04-18
JLT BUGIS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-12-31 | 2022-03-16 | 2022-06-30 | 32 | 2022-04-22 | ACCOUNT NOT IN |  | 2022-04-18
JYH PERTH PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | YI LING CHOO | POH YEN LWI | 2021-06-30 | 2021-07-28 | 2021-11-30 | 8 | 2021-10-08 | KIV | Pending e-filed YA2022 | 2021-09-24
KASSE AUTO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-14 | 2022-06-30 | 32 | 2022-04-29 | ACCOUNT NOT IN |  | 2022-04-25
KASSE AUTO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-14 | 2022-06-30 | 32 | 2022-04-29 | ACCOUNT NOT IN |  | 2022-04-25
KAZBAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2019-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
KAZBAR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2019-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
KIM TECK HONG PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-03-08 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-21
KIM TECK HONG PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-03-08 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-21
KOAH TECHNOLOGIES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2020-09-30 | 2021-12-28 | 2022-03-31 | 15 | 2022-01-14 | REVIEWING - MANAGER |  | 2022-01-10
KOAH TECHNOLOGIES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HWEE JYE CHAN | 2020-09-30 | 2021-12-28 | 2022-03-31 | 15 | 2022-01-14 | REVIEWING - MANAGER |  | 2022-01-10
LE BATH & LIGHT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-07-31 | 2021-10-21 | 2022-01-31 | 20 | 2021-11-12 | INTERIM COMPLETED |  | 2021-11-01
LEGENDARY ENTERTAINMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-07-31 | 2021-12-24 | 2022-01-31 | 30 | 2022-01-21 | ACCOUNT NOT IN |  | 2022-01-03
LEGENDARY ENTERTAINMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-07-31 | 2021-12-24 | 2022-01-31 | 30 | 2022-01-21 | WIP |  | 2022-01-03
LEGENDARY ENTERTAINMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-07-31 | 2021-12-24 | 2022-01-31 | 30 | 2022-01-21 | ACCOUNT NOT IN |  | 2022-01-03
LIKEABLE PETS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-02 | 2022-06-30 | 32 | 2022-03-31 | REVIEWING - MANAGER |  | 2022-03-21
LIKEABLE PETS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-02 | 2022-06-30 | 32 | 2022-03-31 | REVIEWING - MANAGER |  | 2022-03-21
LIKEABLE PETS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-02 | 2022-06-30 | 32 | 2022-03-31 | REVIEWING - MANAGER |  | 2022-03-21
M FLOOR PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-06-30 | 2021-08-31 | 2022-11-30 | 8 | 2021-09-24 | KIV | Pending e-filed YA2022 | 2021-09-06
MA2 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-02-28 | 2021-11-18 | 2021-11-29 | 15 | 2021-11-30 | SENT OUT FOR ADOPTION |  | 2021-11-22
MA2 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-02-28 | 2021-11-18 | 2021-11-29 | 15 | 2021-11-30 | SENT OUT FOR ADOPTION |  | 2021-11-22
MEDIWAY IMAGING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-10-31 | 2022-02-15 | 2022-02-28 | 24 | 2022-02-17 | REVIEWING - MANAGER |  | 2022-02-15
MEDIWAY IMAGING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-10-31 | 2022-02-15 | 2022-02-28 | 24 | 2022-02-17 | REVIEWING - MANAGER |  | 2022-02-15
MEME BISTRO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-06-30 | 2021-11-15 | 2021-12-31 | 30 | 2021-12-10 | KIV |  | 2021-12-01
MEME BISTRO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-06-30 | 2021-11-15 | 2021-12-31 | 30 | 2021-12-10 | KIV |  | 2021-12-01
MEME BISTRO PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-06-30 | 2021-11-15 | 2021-12-31 | 30 | 2021-12-10 | KIV |  | 2021-12-01
MOBILER COMMUNICATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-12-16 | 2021-12-31 | 30 | 2022-01-13 | REVIEWING - MANAGER |  | 2021-12-27
MOBILER COMMUNICATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-12-16 | 2021-12-31 | 30 | 2022-01-13 | REVIEWING - MANAGER |  | 2021-12-27
MOBILER COMMUNICATION PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-12-16 | 2021-12-31 | 30 | 2022-01-13 | REVIEWING - MANAGER |  | 2021-12-27
OCEAN CONTINENTAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-09-30 | 2022-01-20 | 2022-03-31 | 30 | 2022-02-28 | ACCOUNT NOT IN |  | 2022-02-14
OCEAN CONTINENTAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-09-30 | 2022-01-20 | 2022-03-31 | 30 | 2022-02-28 | ACCOUNT NOT IN |  | 2022-02-14
ONE DESIRE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-02-15 | 2022-06-30 | 32 | 2022-03-15 | ACCOUNT NOT IN |  | 2022-03-01
ONE DESIRE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-02-15 | 2022-06-30 | 32 | 2022-03-15 | ACCOUNT NOT IN |  | 2022-03-01
ONE DESIRE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-02-15 | 2022-06-30 | 32 | 2022-03-15 | ACCOUNT NOT IN |  | 2022-03-01
ONLINE STORE NINJAS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-06-30 | 2021-10-29 | 2021-12-31 | 25 | 2021-11-30 | INTERIM COMPLETED |  | 2021-11-01
ORIENT ENERGY SERVICES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-09-30 | 2021-11-30 | 2022-05-31 | 18 | 2021-12-31 | SENT OUT FOR ADOPTION |  | 2021-12-01
RANGOON 99 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
RANGOON 99 PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TEE PEI CHING | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
ROYALPLUS COMMUNICATION PTE LTD | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
ROYALPLUS COMMUNICATION PTE LTD | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-11 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
SAL MARITIME PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-03-31 | REVIEWING - MANAGER |  | 2022-03-28
SAL MARITIME PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-03-31 | REVIEWING - MANAGER |  | 2022-03-28
SAMUEL & CO. PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2019-09-30 | 2021-11-24 | 2021-12-15 | 5 | 2021-12-10 | SENT OUT FOR ADOPTION |  | 2021-12-01
SGP CREDIT | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-12-31 | 2022-02-23 | 2022-04-15 | 16 | 2022-03-17 | SENT OUT FOR ADOPTION |  | 2022-03-14
SHELFORD DEVELOPMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
SHELFORD DEVELOPMENT PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-15 | ACCOUNT NOT IN |  | 2022-04-11
SINTECH PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-07-31 | 2021-12-20 | 2022-01-31 | 10 | 2022-01-14 | PLANNING WITH ACCOUNT |  | 2022-01-11
THE MAKS COMPANY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-02-15 | 2022-06-30 | 24 | 2022-03-04 | REVIEWING - MANAGER |  | 2022-03-01
THE MAKS COMPANY PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-12-31 | 2022-02-15 | 2022-06-30 | 24 | 2022-03-04 | REVIEWING - MANAGER |  | 2022-03-01
THE NIMBLE-GROUP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-08 | REVIEWING - MANAGER |  | 2022-04-01
THE NIMBLE-GROUP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-08 | REVIEWING - MANAGER |  | 2022-04-01
THE NIMBLE-GROUP PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-04-08 | REVIEWING - MANAGER |  | 2022-04-01
TRANS-OCEAN TECHNOLOGY (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-09-30 | 2022-01-20 | 2022-03-31 | 25 | 2022-02-28 | REVIEWING - MANAGER |  | 2022-02-14
TRANS-OCEAN TECHNOLOGY (S) PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | KRISHNAMOORTHY KASIAMMA | 2021-09-30 | 2022-01-20 | 2022-03-31 | 25 | 2022-02-28 | REVIEWING - MANAGER |  | 2022-02-14
VEERAPPAN PROPERTIES PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | POH YEN LWI | 2021-04-30 | 2021-12-01 | 2021-10-31 | 10 | 2021-12-31 | ACCOUNT NOT IN |  | 2021-12-01
VERA CAPITAL PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-12-31 | 2022-03-08 | 2022-03-11 | 20 | 2022-03-15 | INTERIM COMPLETED |  | 2022-03-10
WATCH EXCHANGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2022-04-30 | 2022-03-02 | 2022-03-31 | 40 | 2022-03-29 | REVIEWING - MANAGER |  | 2022-03-21
WATCH EXCHANGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2022-04-30 | 2022-03-02 | 2022-03-31 | 40 | 2022-03-29 | REVIEWING - MANAGER |  | 2022-03-21
WATCH EXCHANGE PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2022-04-30 | 2022-03-02 | 2022-03-31 | 40 | 2022-03-29 | REVIEWING - MANAGER |  | 2022-03-21
WILBIZ PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | LI FANG ANGELA CHAI | 2021-09-30 | 2022-03-09 | 2022-03-31 | 32 | 2022-04-01 | INTERIM COMPLETED |  | 2022-03-28
WWW MEDIA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-18
WWW MEDIA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-18
WWW MEDIA PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | HUI LING PANG | 2021-12-31 | 2022-03-09 | 2022-06-30 | 32 | 2022-03-25 | ACCOUNT NOT IN |  | 2022-03-18
XUAN-U GOURMET PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-09-30 | 2021-12-09 | 2022-03-31 | 30 | 2021-12-31 | SENT OUT FOR ADOPTION |  | 2021-12-13
YEE HO TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | COMPILATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-07-31 | 2022-01-10 | 2022-01-31 | 30 | 2022-02-16 | SENT OUT FOR ADOPTION |  | 2022-02-07
YEE HO TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-07-31 | 2022-01-10 | 2022-01-31 | 30 | 2022-02-16 | SENT OUT FOR ADOPTION |  | 2022-02-07
YEE HO TRADING PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | TAXATION | LOOI YONG KEAN | YI LING CHOO | POH YEN LWI | TIONG YAW TAN | 2021-07-31 | 2022-01-10 | 2022-01-31 | 30 | 2022-02-16 | SENT OUT FOR ADOPTION |  | 2022-02-07