## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | SHARON WONG, PIK EN TOH | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | - Samples (TOC and revenue) sent to client - Pending reply for fieldwork date | 2021-09-13
101 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | - Samples sent to client for Q1 and Q2 - Pending Q3 ML statement | 2021-10-20
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Roll forward AWP and audit programme; Done @ 10/1/2021 | 2021-09-13
1133 MONEYLENDERS PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP) | 2021-10-04
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Roll forward AWP and audit programme - completed on 6/10/2021 | 2021-09-13
1ST CAPITAL PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP) | 2021-10-08
AGRI OILS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | EMILY GOH | JING HE TAN, EMILY GOH | 2022-03-31 |  |  | 16 | 2022-08-31 | ACCOUNT NOT IN | rollover + audit program completed in 16/11/2021 | 2021-11-01
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | JIA XIAN FOONG, SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Report signed, yet to finalise partial AWP and audit program. | 2021-09-14
AK CREDIT CORPORATION PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Contracts received on 02.12. AWP Updated on 09.12 | 2021-11-01
AMEDEO RESOURCES (ASIA) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | XUN HUI SOH | 2019-12-31 | 2020-07-16 | 2020-08-29 | 40 | 2021-06-30 | PENDING DOCS & PAYMENT | Pending payment and document Pending letter of support from Holding Company Email Follow up: 14/12/2020 Email follow up: 22/112021 | 2020-07-16
ASIAN GOLF INDUSTRY FEDERATION | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PUI SHI LEE | 2021-06-30 | 2021-09-29 | 2021-12-31 | 80 | 2021-12-31 | PENDING PAYMENT | Pending 5 copies of signing pages | 2021-10-06
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | - Pending documents from client | 2021-09-14
AVIS CREDIT (SG) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP) Pending client reply to provide loan samples | 2021-10-16
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | PIK EN TOH, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | - Samples (TOC and revenue) sent to client - Fieldwork on 11 and 12 November 2021 to vouch on expenses and other income, TOC and revenue | 2021-09-14
BAN KING CREDIT (S) PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PIK EN TOH | HAO YAN, PIK EN TOH | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | - Samples sent to client to prepare for Q1 - Q3 - Fieldwork on 11 and 12 November 2021 to vouch | 2021-10-16
BITMEX TOKEN SERVICES PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHAI KIT MAN, WEI QI YU | 2021-12-31 | 2022-05-16 | 2022-07-31 | 40 | 2022-07-31 | WIP |  | 2022-05-19
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | JUN LOKE, PUI SHI LEE, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Roll forward AWP and audit programme - completed on 29/10.2021 | 2021-09-20
CASH CHECK SINGAPORE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PUI SHI LEE | EMILY GOH, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP) | 2021-09-27
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | SHARON WONG, YONG LAI WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Interim audit done. WIP started on 30.03 Updated on 04.04 | 2021-09-15
CASHMAX CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP). Received softcopies for selected contracts. Overall contract checked. only few need to get additional supporting from client. Updated 0n 14.10 | 2021-10-24
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | XUN HUI SOH | YU XUEN NG | 2019-12-31 | 2020-10-12 | 2020-11-30 | 60 | 2021-11-30 | PENDING DOCS | 2. Follow up on 24/11/21 1. Pending signing doc. Follow up on 23/8 | 2020-10-29
CHIC CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2020-12-31 |  |  | 60 | 2021-11-19 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
CONVERSANT GLOBAL PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SAMANTHA WONG, PIK EN TOH, PUI SHI LEE | 2021-12-31 | 2022-04-11 | 2022-07-31 | 120 | 2022-06-20 | FINALIZING | 2. Samantha to fill up the audit programme 1. Management account received on 11 April 2022 | 2022-05-04
CONVERSANT PARTNERS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH, WEI QI YU | 2021-12-31 | 2022-04-11 | 2022-07-31 | 40 | 2022-06-20 | WIP | Management account received on 11 April 2022 | 2022-05-04
CONVERSANT PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH, WEI QI YU | 2021-12-31 | 2022-04-11 | 2022-07-31 | 160 | 2022-06-20 | WIP | Management account received on 11 April 2022 | 2022-05-04
CONVERSANT SOLUTIONS PTE. LTD. | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PIK EN TOH, PUI SHI LEE | 2021-12-31 | 2022-04-11 | 2022-06-20 | 160 | 2022-06-20 | WIP | Management account received on 11 April 2022 | 2022-05-04
FUTURIX PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SHWU WEI KHOR, PIK EN TOH | 2022-03-31 | 2022-06-09 | 2022-08-31 | 100 | 2022-08-31 | PLANNING WITH ACCOUNT |  | 2022-06-15
HDR PAYMENTS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, WEI QI YU | 2021-12-31 |  |  | 80 | 2022-07-31 | WIP | Roll forward for awp and audit program done | 2021-11-10
HDR SG PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, WEI QI YU, JING HE TAN, EMILY GOH | 2021-12-31 |  |  | 16 | 2022-07-31 | WIP | roll over + audit program completed on 16/11/2021 | 2021-11-01
KHALON & GILL MONEYLENDERS PTE. LTD. | ACUMEN ALPHA ADVISORY PTE. LTD. | ACCOUNTING | LOOI YONG KEAN | XUN HUI SOH | JING HE TAN | JING HE TAN | 2021-12-31 | 2022-01-12 | 2022-02-28 | 40 | 2022-01-25 | REVIEWING - PARTNER |  | 2022-01-24
LOH BROTHERS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | YEE YONG KONG, WEI QI YU, EMILY GOH, HAO YAN | 2021-03-31 | 2021-10-25 |  | 80 | 2022-01-31 | SIGNED | 2. Kelvin assist to fill up the audit programme 1. Roll forward for awp and audit program done | 2021-11-10
LUMINOUS DENTAL @ RAFFLES PLACE PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ 201D TAMPINES PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ 25A CHAI CHEE PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ 821 TAMPINES PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ BEDOK MALL PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ BEDOK SOUTH PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ CHAI CHEE PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ HOUGANG PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ NEW UPPER CHANGI PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ PASIR RIS PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ TAMPINES PLAZA PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ TAMPINES PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ YISHUN PL | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL GROUP HOLDINGS PTE. LTD. | ACUMEN ASSOCIATES LLP | ROLL-OVER | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | YEE YONG KONG, SAMANTHA WONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
NOVOTEC EDM SUPPLIES PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, JIA XIAN FOONG | 2021-12-31 | 2022-02-10 | 2022-03-31 | 80 | 2022-06-30 | PENDING DOCS | Sent for adoption on 31.03 Updated on 04.04 | 2021-11-09
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | sent for adoption on 30.03 with outstanding sections. Updated on 04.04 | 2021-09-22
OASIS CREDIT SERVICES PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | JUN LOKE, HAO YAN, YONG LAI WONG, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP); AUP Q1Q2 done | 2021-10-11
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | YONG LAI WONG, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | SENT OUT FOR ADOPTION | Interim audit done. Pending final account. updated on 04.04 | 2021-09-23
POWER CREDIT ENTERPRISE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | YONG LAI WONG | HAO YAN, YONG LAI WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SENT OUT FOR ADOPTION | Quarter 1 and quarter 2 (interim AUP). Sample selection sent, awaiting client to prepare. Updated on 28.10. | 2021-10-20
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 40 | 2022-03-31 | SIGNED | Interim AUP (Q1, Q2 and Q3) completed AUP fee for 3 quarters paid (S$1020) | 2021-09-24
RAFFLES CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | PIK EN TOH | YEE YONG KONG, PIK EN TOH, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | 3. Kelvin assist to fill up the audit programme. 2. Interim audit (for the period from 1/1/2021 - 30/9/2021) completed 1. Interim billing paid (S$2550) | 2021-09-24
RUSSELL ROCKS PTE LTD | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, HAO YAN | 2021-12-31 | 2022-02-14 | 2022-06-30 | 80 | 2022-02-28 | CLEARING REVIEW POINTS | Roll forward for awp and audit program done | 2021-11-10
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, HAO YAN | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Roll forward AWP and audit programme; Done for AWP and audit program | 2021-09-24
SANDS CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, SHARON WONG | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP) | 2021-09-24
SCDA ARCHITECTS PTE LTD | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, WEI QI YU, JIA XIAN FOONG | 2021-12-31 |  |  | 80 | 2022-06-20 | WIP | Roll forward of AWP | 2021-11-09
SCDA DESIGN PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, WEI QI YU, HAO YAN | 2021-12-31 |  |  | 150 | 2022-06-20 | WIP | Roll forward for awp and audit program done | 2021-11-10
SCDA INTERIORS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, WEI QI YU, ZHEN KANG LAU, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-06-22 | WIP | roll over | 2021-11-01
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | JING HE TAN, WEI QI YU, EMILY GOH | 2021-12-31 |  |  | 80 | 2022-03-31 | SIGNED | Roll forward AWP and audit programme - completed on 28/10/21 | 2021-09-27
SINCERE MONEYLENDER PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM SWEE HUA | XUN HUI SOH | WEI QI YU | EMILY GOH, WEI QI YU | 2021-12-31 |  |  | 40 | 2021-12-31 | SIGNED | Quarter 1 and quarter 2 (interim AUP) | 2021-10-12
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 80 | 2022-03-31 | SENT OUT FOR ADOPTION | Roll forward AWP and audit programme 1.) Completed the roll forward for AWP 2.) In progress the roll over for audit program | 2021-09-27
SME CARE PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LOOI YONG KEAN | XUN HUI SOH | PUI SHI LEE | SHARON WONG, PUI SHI LEE | 2021-12-31 |  |  | 40 | 2021-10-04 | SENT OUT FOR ADOPTION | Quarter 1 and quarter 2 (interim AUP) 1.) No interim AUP for SME care, no loan issue as at June 2021 | 2021-09-27
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | PUI SHI LEE, JIA XIAN FOONG | 2021-12-31 | 2022-04-11 | 2022-07-31 | 80 | 2022-06-20 | ACCOUNT NOT IN | 2. Swiftserve assigned to Pui Shi 1. Jia xian roll forward of AWP | 2021-11-19
SWIFTSERVE PTE LTD | ACUMEN ASSURANCE | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | YEE YONG KONG, PIK EN TOH, PUI SHI LEE | 2021-12-31 | 2022-04-11 | 2022-07-31 | 80 | 2022-06-20 | REVIEWING - MANAGER | 2. Kelvin assist to fill up audit programme 1. Management account received on 11 April 2022 | 2022-05-04
SYNERGY LI CAPITAL PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | HAO YAN | HAO YAN | 2021-03-31 |  |  | 150 | 2022-06-30 | ACCOUNT NOT IN | Roll forward for awp and audit program done | 2021-11-10
SYNERGY LI INTERNATIONAL RESOURCES LIMITED | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | EMILY GOH | EMILY GOH | 2021-03-31 |  |  | 16 | 2022-06-30 | ACCOUNT NOT IN | roll over | 2021-11-01
TECHNIDRILL AUSTRALASIA PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PUI SHI LEE | PUI SHI LEE, JIA XIAN FOONG | 2021-12-31 | 2022-01-10 | 2022-02-28 | 80 | 2022-02-28 | PENDING DOCS | Account received on 10 January 2022, assigned to Pui Shi. Jia Xian Roll forward of AWP | 2021-11-09
THE MASONIC HALL BOARD LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | WEI QI YU | WEI QI YU, SAMANTHA WONG | 2021-12-31 |  | 2022-08-31 | 80 | 2022-07-31 | ACCOUNT NOT IN | 1. Samantha to roll AWP on 10 June 2022 | 2022-06-10
THREE FINS PTE. LTD. | SYA PAC | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | CHIA EN CHEONG | CHIA EN CHEONG, WEI QI YU | 2021-12-31 |  |  | 120 | 2022-07-31 | WIP |  | 2022-04-28
UNIQCASH PTE. LTD. | ACUMEN ASSURANCE | PMFT AUDIT | LIM SWEE HUA | XUN HUI SOH | KOK YEE CHOONG | KOK YEE CHOONG |  | 2021-02-22 | 2021-04-30 | 20 | 2021-05-31 | FINALIZING | PMFT report obtained. will schedule one day for wrapping up. | 2021-02-22