## Sheet1
Client | Firm | Job Type | Partner | Manager | Leader | Assistant | FYE | Acount Received | Due Date | Budget Hours | Expected Completion Date | Status | Remark | Create On | Complete Date
1 1 8 CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | PAI NEE WONG | JACINTH LOI KAI CHEE | SAMANTHA WONG, HAO YAN, EMILY GOH | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | PENDING DOCS | TOC & TOD pending to finalize | 2021-09-01
BAZE MARINE & OFFSHORE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | PAI NEE WONG | JACINTH LOI KAI CHEE | YEE YONG KONG, WAI KEONG SHUM | 2022-03-31 | 2022-06-08 | 2022-09-30 | 70 | 2022-07-15 | CLEARING REVIEW POINTS |  | 2022-06-29
GT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | QUARTERLY STATEMENT REVIEW | LIM NIAW YUN | PAI NEE WONG | JACINTH LOI KAI CHEE | JACINTH LOI KAI CHEE, EMILY GOH | 2021-12-31 | 2021-09-14 | 2021-10-31 | 20 | 2021-10-31 | PENDING PAYMENT |  | 2021-09-20
GT CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM NIAW YUN | PAI NEE WONG | JACINTH LOI KAI CHEE | SAMANTHA WONG, JACINTH LOI KAI CHEE, JUN LOKE, EMILY GOH, KWEH CHUN SHENG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 60 | 2021-10-31 | PENDING PAYMENT | TOC & TOD pending to finalize, pending payment | 2021-09-01
HAPPY CASH PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | EK NA HENG, JUN LOKE, EMILY GOH, SHARON WONG | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | PENDING DOCS | Report signed & payment received on 29/6/2022 Pending archive | 2021-09-01
IVAN INSURANCE BROKERS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | YEE YONG KONG, JACINTH LOI KAI CHEE | 2021-12-31 | 2022-01-24 | 2022-06-30 | 80 | 2022-05-22 | PENDING DOCS | Audit programme pending to finalize | 2022-02-15
LUMINOUS DENTAL @ RAFFLES PLACE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, EK NA HENG, WEI QI YU, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ 201D TAMPINES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SUET YEE CHEONG, PIK EN TOH, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ 25A CHAI CHEE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, SUET YEE CHEONG, WEI QI YU, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ 821 TAMPINES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SUET YEE CHEONG, PIK EN TOH, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ BEDOK MALL PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | SHWU WEI KHOR, JACINTH LOI KAI CHEE, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ BEDOK SOUTH PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, SHWU WEI KHOR, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | PLANNING WITHOUT ACCOUNT |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ CHAI CHEE PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | PIK EN TOH, SUET YEE CHEONG, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ HOUGANG PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, SHWU WEI KHOR, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ NEW UPPER CHANGI PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, SHWU WEI KHOR, WEI QI YU, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ PASIR RIS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, EK NA HENG, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ TAMPINES PLAZA PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | JACINTH LOI KAI CHEE | SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ TAMPINES PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, EK NA HENG, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL CLINIC @ YISHUN PL | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | JACINTH LOI KAI CHEE, EK NA HENG, SAMANTHA WONG, YEE YONG KONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
LUMINOUS DENTAL GROUP HOLDINGS PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | WOELLY WILLIAM | XUN HUI SOH | PIK EN TOH | EK NA HENG, JACINTH LOI KAI CHEE, YEE YONG KONG, SAMANTHA WONG | 2018-12-31 | 2022-06-01 | 2022-06-30 | 100 | 2022-07-15 | ACCOUNT NOT IN |  | 2022-06-07
MM CREDIT PTE. LTD. | ACUMEN ASSOCIATES LLP | STATUTORY AUDIT | LIM SWEE HUA | PAI NEE WONG | JACINTH LOI KAI CHEE | YEE YONG KONG, EK NA HENG, EMILY GOH, HAO YAN | 2021-12-31 | 2021-09-01 | 2021-10-31 | 40 | 2021-10-31 | PENDING DOCS | TOC & TOD pending to finalize | 2021-09-01